Ongoing Programme of Action

Monitoring Report

March 2008

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

# Contents

Contents	1

Summary	2

Highlights	2

Leadership	2

Changing Attitudes and Behaviour	3

Ensuring Safety and Accountability	4

Effective Support Services	4

Hotspots	5

Variations	5

Alerts	5

Monitoring Report	7

Three month summaries	9

Leadership	9

Changing Attitudes and Behaviour	19

Ensuring Safety and Accountability	24

Effective Support Services	26

Detailed Milestone Updates	29

Leadership	29

Changing Attitudes and Behaviour	41

Ensuring Safety and Accountability	48

Effective Support Services	51

How this report works	55

# Summary

- The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions, which were consolidated to 52 actions. Work is either complete or ongoing for these actions and are not reported on in this report.

- The Taskforce’s Ongoing Programme of Action (OPOA) consists of 31 objectives, which form the Taskforce’s work programme. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

- Any variation to objectives or actions requires a formal variation. A variation template will need to be completed and signed by the appropriate Taskforce member and then forwarded to Secretariat. The Secretariat will then forward it on to the Taskforce Chair for approval. Completed variations are kept by the Secretariat for referral if required. For more information on this report, how it is organised and the formal variation process refer to the “How this report works” section at the end of the document.

Objective status

| Total number of objectives | 31 |
| --- | --- |
| On track | 24 |
| Variations | 3 (pending) |
| Alerts | 4 |

## Highlights

This section provides an overview and points of note for the reporting period of September 2007 to February 2008.

### Leadership

### Maori Programme of Action

- The Taskforce’s Maori Reference Group (MRG) and the Ministry of Social Development are jointly leading development of a Maori Programme of Action, which will form part of the Taskforce’s Ongoing Programme of Action.

- The MRG are holding a Family Violence Whanau Summit on 3-4 April 2008 in the Waikato. The Summit will be co-hosted by Tainui and King Tuheitia, and will bring together Maori leaders to discuss the issues that affect whanau, to share current knowledge of issues and solutions, and to develop a plan for the future. The outcomes from the Summit will feed into the development of a Maori Programme of Action.

- The Summit theme is “E tu! Taking Action!”. The purpose of the Summit is to:

- get leadership at key levels within Te Ao Maori to prioritise the importance of whanau

- identify solutions and actions that can both be undertaken by whanau, hapu and iwi, and that will also feed into the development of a programme of action.

### Domestic Violence Act 1995 review

- The Ministry of Justice is currently reviewing the Domestic Violence Act 1995 (DVA) and related legislation.  Although not driven by the Taskforce, this review aligns closely with the Taskforce’s direction and impacts on much of the Taskforce’s work.

- The review focuses on matters that will improve the current law in achieving its objective of reducing and preventing violence in domestic relationships.

- A discussion document on the review was released on 11 December 2007. The discussion document contained 27 issues with preliminary proposals and 55 questions for submitters to consider.  Public submissions closed on 13 February 2008.

- Following the analysis of the submissions, papers will be developed with policy proposals for amendments to the DVA and related legislation for consideration by the Government in May 2008.

- If proposals are approved it is anticipated that the Ministry will have legislation drafted and ready to be tabled in the House in July 2008.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

- The second phase of the Campaign for Action on Family Violence focuses on stories of positive change, particularly on intimate partner violence and the benefits to be gained by choosing to be violence free in terms of relationships with partners and children.

- The second phase was launched on 14 February 2008. The new advertisements, featuring four men telling their stories, went to air on 17 February 2008.

- The 0800 information line and the website have shown marked increases in traffic since the launch of the second phase, and there have been many requests for resources associated with the Campaign.

- To continue monitoring the effect of the Campaign, a second reach and retention survey is to take place in March and April 2008. A survey at the end of 2007 showed that a very high proportion (87%) of those asked had remembered the campaign and more than half of those people had also discussed the campaign with someone and/or taken action as a result.

### Family Violence Death Reviews

- On 13 February 2008, the Government considered and approved a paper from the Minister of Health regarding the Family Violence Death Reviews project. The purpose of the paper was to seek agreement to establish a Family Violence Death Review Committee (FVDR Committee) under the New Zealand Public Health and Disability Act 2000.

- The paper was a result of the Taskforce accepting the Ministry of Health’s recommendation for a "formal mechanism for interagency, multidisciplinary systematic review of family violence-related deaths be established under the New Zealand Public Health and Disability Act 2000”.

- The recommendation to establish a FVDR Committee was developed through the interagency Family Violence Death Review project, led by the Ministry of Health in collaboration with the Ministries of Social Development and Justice, the Police and other key government and non-government organisations.

- The Ministry of Health is aiming to establish the FVDR Committee by the end of June 2008. The terms of reference are currently being defined and the interagency Implementation Advisory Group is being established, with their first meeting scheduled for May 2008.

### Ensuring Safety and Accountability

### Protection Orders system efficacy

- An effective Protection Orders system is a key part of building a secure, responsive protection system. Swift and unambiguous action by the police and the courts will increase the chances of securing safety for victims and accountability for perpetrators.

- In August 2007, the research report Living at the Cutting Edge: Women’s Experiences of Protection Orders was released. This research report was commissioned by the Ministry of Women’s Affairs, and conducted by Waikato University.

- Following the release of the report the Minister for Social Development and Employment sought a response to the report from the Taskforce.

- On 17 December 2007 the Taskforce submitted their response to the Minister for Social Development and Employment. The Minister agreed with the Taskforce’s recommendations, and distributed the report to members of the Family Violence Ministerial Team and the Minister of Immigration.

- The Ministerial Team discussed the report at the meeting of 13 March 2008.

### Family Violence Courts

- National Operating Guidelines for Family Violence Courts have been developed. These Guidelines:

- have been approved by the Chief District Court Judge

- have been distributed to the Family Violence Court Judges for their consideration

- will go to a broader consultation in March 2008

- will be implemented by mid 2008, with training currently being developed.

### Effective Support Services

### Pathway to Partnership

- The Pathway to Partnership initiative sits within the Taskforce’s Effective Support Services theme, and was initiated in the Taskforce’s first Programme of Action.

- In 2006, work was started on a long-term plan to improve the capacity, capability and sustainability of service providers delivering family violence related services to New Zealand’s children and families.

- On 12 February 2008, the Government announced new funding for community organisations with existing contracts to provide essential services for families, children and young people. This will build on work that is already under way, for example simplifying funding and contracting processes, moving some services from contracts to grants to reduce compliance costs, and multi-year funding to provide more security.

- Funding provision for essential NGO and community services will impact on many objectives of the Taskforce’s Ongoing Programme of Action.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk. All objectives not mentioned in this section are on track to be completed as planned.

### Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 3.3 | Social Service Supporting Courts | The objective remains the same, with changes to the actions required. The variation has been requested due to the need to align with the direction the Chief District Court Judge has set for the Family Violence Courts, and to ensure consistency with a 2008 Budget bid. | To be considered by the Taskforce chair. |
| 2.4 | Curriculum development | Changes are required to actions, although not the objective. “Whole school strength based approaches” cannot be extended due to an increase in costs for delivery of student wellbeing contracts. The use of this approach will be strengthened by incorporating successful professional learning approaches for student wellbeing in the design and delivery of ongoing professional development contracts. | To be considered by the Taskforce chair. |
| 1.10 | Pacific Research Agenda | Changes required to actions, although the objective will remain the same. Further development of the project plan has clarified actions required to achieve Taskforce objectives. | Variation due to be submitted before 9 April 2008 Taskforce meeting. |

### Alerts

This table highlights areas that have been identified as at risk of not being delivered.

| Objective | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 1.1a | Mapping of the Ongoing Programme of Action | The objective and actions for this work need to be clarified. | The Secretariat will seek clarification from Taskforce members about this work. |
| 2.1 | Kia Puawai | An early years budget package was developed and submitted to the Minister of Finance in December 2007. This package was considered by ‘Families Young and Old’ Ministers at their meeting in March 2008. There has been some delay on this objective while the budget package was developed. | Work on building an effective early years intervention system continues. Budget decisions impact only on the scope of some initiatives. |
| 2.2 | Improving Attachment | A variation may be required as the Auckland DHB has decided not to proceed with the pilot to prevent Shaken Baby Syndrome. Initial scoping highlighted issues with the pilot site. | The Ministry of Health has been approached to fund a regional pilot and is currently considering the possibility. |
| 4.2 | Pacific Service Workforce Development | This project plan is now part of development of Pathway to Partnership work on workforce provider capacity and capability. The project plan has not yet been finalised as the Pathway to Partnership project plan is currently being formulated after the funding announcement on 12 February 2008. | Pathway to Partnership project plan is currently being clarified and confirmed, and is due to be ready for implementation in July 2008. |

# Monitoring Report

The Three Month Summaries section provides an update on work undertaken in the previous three months and work which is upcoming in the next three months.

The Detailed Milestone Updates section shows the work that has progressed for each milestone in table format.

## Three month summaries

This section provides background and updates on work undertaken in the previous three months and work planned for the upcoming three months.

### Leadership

1.1 Facilitation of the Ongoing Programme of Action (OPOA) Lead agencies: All agencies and the Secretariat

Background Due to ad hoc work there was no monitoring report required for the 6 December Taskforce meeting. The Secretariat undertook a stock-take of work on the first Programme of Action in January 2008, in order to assess the status of the ongoing work that either led to the work outlined in the OPOA or is continuing and has become “business as usual” within each agency. Progress to date (previous 3 months work) Agencies were contacted in January to update on work of the first POA in short table format. This also proved useful in preparation of media information for the release of the OPOA on 14 February 2008. Distribution of the Ongoing Programme of Action in the latter half of February after the release. Work on gaining updates for the Monitoring Report due to the Taskforce for the 9 April meeting. Current ongoing work (next 3 months) Drafting and completing the monitoring report for the 9 April meeting of the Taskforce. The monitoring report will go to the Family Violence Ministerial Team, as requested in late 2007. Further development of milestones required for many objectives for the next Monitoring Report, which is due for the 4 June Taskforce meeting. The June report is likely to include updates from the first Programme of Action, to be confirmed. Meet with agencies if required. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.1a Mapping of the Ongoing Programme of Action (OPOA) Lead agency: NGOs

Alert: Next steps to be confirmed.

1.2 Maori Programme of Action (MPOA) Lead agency: The Maori Reference Group and the Ministry of Social Development.

Background The Taskforce’s Maori Reference Group (MRG) is developing goals and messages that will form the shape of its MPOA. A key priority in achieving this is to bring together Maori leaders of note who will encourage the end of family violence within Maori communities. To this end a Whanau Summit has been organised to raise family violence awareness within this leader group. Following the Summit, MRG will co-ordinate and facilitate regional hui to disseminate the Summit findings and outcomes, and to ensure the ownership of the MPOA as it progresses to its launch in June 2008. Progress to date (previous 3 months work) MRG has developed its Communication Strategy for the Summit and has been working towards the finalisation of its plans for the Summit and confirming details in readiness for the event. Care has been taken on the Summit programme to ensure the messages are delivered succinctly. MRG has also been developing the regional hui strategy and identifying the areas of focus for these hui. Current ongoing work (next 3 months) Staging of the Whanau Summit which is to take place on 3-4 April 2008 in Ngaruawahia and Hopuhopu in Waikato, and will be co-hosted by Tainui. Progressing the MPOA, which will also include outcomes from the Summit. Undertaking and completing Regional Hui. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.3 Pacific Programme of Action (PPOA) Led agency: The Pacific Advisory Group and the Ministry of Social Development

Progress to date (previous 3 months work) A draft Pacific POA, which includes a communications plan, has been developed. It has been circulated to members of the Taskforce’s Pacific Advisory Group (PAG) for comment. A process to consult with stakeholders has been developed. Implementation of this process has commenced. In November 2007, PAG coordinated a Pacific launch of the ‘It’s not OK’ campaign as a call for Pacific communities to work together to address family violence. Components of the Pacific communications plan were implemented. This included posters, radio advertisements, community event sponsorship and television coverage. Current ongoing work (next 3 months) Consultation with key stakeholders will commence. Final comments will be incorporated into the Pacific POA. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.4 Child abuse Lead agency: Office of the Children’s Commissioner

Background As agreed in the Ongoing Programme of Action, by June 2008, the Taskforce will: - develop a work programme on child abuse (including child sexual abuse) that: - focuses on improving outcomes for children - takes account of the different types of child abuse - identifies priority areas where the Taskforce can make a difference. It was decided that work would begin with an overview of child sexual abuse, summarising the issue and current response. This is because work had already begun specifically on this area of abuse when the scope of the Taskforce’s work was extended to child abuse. Work is now underway on the other types of abuse. Progress to date (previous 3 months work) - Early draft paper (Child Sexual Abuse: An Overview of the Issue and Current Response) circulated to Taskforce for discussion at 6 December 2007 Taskforce meeting. - Comment was also sought from other agencies and incorporated, additional information was located and incorporated as necessary. - A final draft was circulated in February 2008 and is now provided to the Taskforce for noting at its 9 April meeting. Current ongoing work (next 3 months) - Agree scope for work on other types of child abuse. - Gather and collate literature on the issue and information on services on the other types of child abuse. - Consult with relevant agencies on services available and work programme planning in order to develop and agreed work programme by June 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.5a Family Violence Free Workplaces Lead agency: Ministry of Social Development

Overall Context The current Human Resources plan to support the goal of becoming a family violence free workplace involves a longitudinal approach founded on raising and maintaining staff awareness of family violence - the workplace impacts and supports. The plan also adopts one of the Te Rito (New Zealand Family Violence Prevention Strategy 2002) principles which describes a continuous improvement approach to family violence prevention – “Family violence prevention initiatives should be continually enhanced as information and better ways of working are identified”. The plan involves developing a family violence policy and initial support mechanisms (eg information and resources, and referral options through the Employee Assistance Programme provider). The next stages involve identifying and building further support mechanisms for staff and managers. Underpinning this work is the ongoing awareness raising initiatives which includes information sessions, posters, and “family violence” messages through Corporate communication channels. Consistent with the Te Rito principle we will also continue to enhance initiatives as information and better ways of working are identified. This will involve testing or piloting some initiatives (such as peer support groups) and information sharing across other Taskforce contributors (ACC and NZ Police). 1.5a.2 Policy development Background The purpose of the family violence policy is to raise awareness of the impact of family violence on the workplace and to provide and raise awareness of the support mechanisms for employees who are experiencing family violence, want assistance to help others, or want assistance to stop their violence. Progress to date (previous 3 months work) A draft family violence policy (awareness and support in the workplace) has been completed. This has been shared with ACC and NZ Police. Current ongoing work (next 3 months) The policy stills needs to go through the Ministry approval and sign-off process. The plan was to progress this through a steering group but there were delays in establishing this group. The work over the next 3 months is to progress the draft policy through an appropriate approval process and plan for its implementation. Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.3 Establish internal steering group to oversee Family Violence initiatives Background Many parts of the Ministry are involved in Family Violence related policy and service delivery initiatives. It is also important that the HR policy and support mechanisms are appropriately championed. It was planned to establish a Steering Group made up senior Ministry staff. Progress to date (previous 3 months work) An initial agreement to establish the Steering Group was obtained but one of the members left the Ministry and has only recently been replaced. There is also a current concern about the number of Steering Groups operating across the Ministry and this may require a reconsideration of this governance approach. Current ongoing work (next 3 months) Either re-establish the Steering Group or identify an alternative structure for providing high-level direction and approvals. Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.4 Manager guidelines developed to support policy Background It is important that managers have access to appropriate information and resources to be able to support their staff if they are approached about family violence issues. The manager guidelines have been developed as a companion resource to the family violence policy. Progress to date (previous 3 months work) The manager guidelines have been developed and will be implemented subject to approval of the family violence policy. Current ongoing work (next 3 months) Will be progressed in conjunction with 1.5a.2 Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.5 Regional information sessions Background The information sessions are part of the broader “family violence awareness raising” activities. Progress to date (previous 3 months work) Following the family violence information sessions for national office staff it was agreed that similar information sessions would be provided for regional staff. It should be noted that many staff in the Work and Income service line and the Child, Youth and Family service line have already had specific family violence training or awareness sessions as part of their service delivery roles. The intent is to provide the information sessions to other regional staff that might not already have had the opportunity to receive or attend training or information sessions on family violence. Current ongoing work (next 3 months) We are exploring delivery options for family violence information sessions for regional staff. A key consideration is how to deliver information sessions in a “sustainable way” as opposed to a one-off “event”. This may link with 1.5a.7 (tools and resources) and the possible development of online resources. We will canvas demand for regional information sessions and develop responses accordingly. This may result in exploring different delivery options – such as the development of relevant FAQ sheets about family violence rather than a presentation-style information session. Timing / Ongoing / Recommendations / Conclusions Status = on track. Timing will likely vary in response to feedback from service lines and business groups about the demand for regional family violence information sessions. 1.5a.6 Providing accessible information and resources Background Information on family violence not only supports employees who are experiencing family violence, but also enables other employees to develop an increased understanding of their co-workers who are in this situation. Progress to date (previous 3 months work) The Ministry has been able to launch its own family violence awareness raising activities in conjunction with the launch of the family violence social marketing campaign (Family Violence - It’s Not OK). Information and links have been placed on the Ministry intranet for staff under Resources for Employees/Your health and wellbeing/Family Violence, with the “It’s Not Ok” logo placed on the front page of the Ministry intranet as a link to information and resources for staff. Information on the Work and Income Peer Support Network (refer 1.5a.9) has also recently been placed on the intranet. Family violence posters (from the Campaign) were distributed to business units in National Office to display, and are displayed prominently in the entrance way to the Bowen State building in National Office. Corporate MSD included a family violence message as part of 2008 MSD calendar focusing on the theme of Family and Community. The “flip-side to January08” was a family violence-themed message and information for seeking help. The calendar was distributed to staff in Dec 2007. Current ongoing work (next 3 months) We will continue to explore other opportunities to raise visibility of family violence. This will be developed as part of a communication plan for 2008 which will identify opportunities to raise awareness and maintain the profile of violence family-related initiatives. Timing / Ongoing / Recommendations / Conclusions Status = on track. 1.5a.8 Training Progress to date (previous 3 months work) In-depth family violence training for line HR staff and HR consultancy team members was delivered by Preventing Violence in the Home (PVH) in September 2007. This was essentially a comprehensive information session to raise awareness of family violence issues and complexities for the Human Resources staff that primarily support the Ministry’s managers. The Work and Income service line of the Ministry is piloting a family violence peer support network (refer 1.5a.9). The peer support programme was launched in Dec 2007 with 13 staff who will provide in-house support on family violence, personal matters and information on EAP services to Work and Income staff. Work and Income developed and tailored a peer support training programme which was delivered at the end of 2007. Current ongoing work (next 3 months) No specific training is planned for the next three months. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.5b Family Violence Free Workplaces Lead agency: ACC

Progress to date (previous 3 months work) In September the Family Violence intranet site was published, with supporting resources also made available. Work on the Family Violence Policy took place in November 2007, and is currently continuing. A refresh launch of policy and guidelines, Family Violence Support, took place in February 2008. ACC is working with Preventing Violence in the Home (PVH) to adapt the tools used in training for human resources staff within the Ministry of Social Development so they are relevant for ACC. An initial half-day pilot training by PVH took place in early 2008, however this was found not to meet the needs of the organisation. Modifications, or an alternative supplier, are being investigated. Current ongoing work (next 3 months) Continuing work on developing training for staff. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.5c.1 Family Violence Free Workplaces Lead agency: NZ Police

Progress to date This project has been added onto the Police HR work programme. To date Police have held meetings with MSD to discuss the approach used for this project, as they are considerably further down the track of developing a family violence free workplace policy and support programme. Next Steps - A meeting scheduled for 17 March 2008 with MSD and ACC has been requested to discuss the approach other agencies are using to progress work - collaborating and sharing where appropriate. - A draft policy is being written for consultation with the family violence team and the policy group - this draft policy will be consulted and will be reported upon by the end of March Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.6 Iwi-led crime prevention Lead agencies: NZ Police

Background There are 11 major work streams in Effective Intervention (EI), each of which corresponds to an initial Cabinet paper. The bulk of efforts to reduce offending and imprisonment among Māori are concentrated in work stream 11 [“Paper 11: Māori and Pacific peoples” [POL (06) 179 and CAB (06) 280 refer]. As part of this work stream, Police, Te Puni Kōkiri and the Ministry of Justice in consultation produced a Programme of Action for Māori (PoAfM) [CBC Min (06) 22/12 refers – interim; POL Min (07) 8/6 refers - final]. Around the same time as the PoAfM was being developed, Police Commissioner Howard Broad presented a draft of the Police Responsiveness to Māori strategy to his Māori Focus Forum. Those iwi leaders used the opportunity to advocate for Police support in constructing their own ICPPs, under the umbrella of a New Zealand Māori Crime Reduction Strategy (NZMCRS). Subsequently, officials from Police and Te Puni Kōkiri agreed to work on the NZMCRS together and include it as a major component of the PoAfM - this was agreed by Cabinet Policy Committee in May 2007 [POL Min (07) 8/6 refers] and confirmed by Cabinet on 7 May 2007 [CAB Min (07) 15/1 refers]. Progress to date (previous 3 months work) In mid 2007 Police and Te Puni Kökiri began consulting with iwi on the Iwi-led Crime Prevention Plans (Iwi Plans). A number of Hui have been held nationally and attended by Police and Te Puni Kökiri officials and a mixture of iwi delegates, urban authorities and Mäori service providers. The purpose of these meetings has been to: - gauge support for the Iwi Plans - provide background and contextual information on the Iwi Plans - identify possible barriers for development and - begin to define the criminal justice profiles for iwi. Police and Te Puni Kökiri have been supporting iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: - providing Police intelligence to iwi groups that enable iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas. - providing specialised trained staff who are able to take iwi through a formal problem solving approach to crime prevention crime prevention methodology training in SARA and POP models - providing draft Iwi Crime Prevention Plan templates and Guidance Notes for preparation of the Iwi Plans - funding writers nominated by iwi to begin drafting iwi-specific crime prevention plans. Current ongoing work (next 3 months) Police are currently working with iwi in six Police districts (through individual workshops) to support them in "trailblazing" this work, while work continues across the remaining six Police districts with ongoing dialogue between Police and major iwi groups. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.7 Family Violence Clearinghouse Lead agency: Ministry of Social Development

Progress to date (previous 3 months work) 1.7.1 The legal team have provided their final input into the contract, which is now in final draft state and ready for approval. Management are to consider the option to extend the length of the contract until a new approach / strategy is implemented. 1.7.2 Work has commenced on gathering requirements for a new NZFVC. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.8 Case studies characterising good practice Lead agency: Ministry of Social Development

Background Current evaluative activities will be used to identify good practice models. The project will commence by drawing on one of the evaluative activities that support The Campaign for Action on Family Violence (the Campaign). The aim of the evaluation project is to investigate and illustrate the impact of the Campaign on selected communities. It will focus on collecting information on observable and recorded changes relating to family violence over time in selected communities. As part of this evaluation two case studies will be produced that illustrate and explain “significant changes” arising from the Campaign. The case studies, characterising good practise, will therefore focus on the practice of family violence prevention through social marketing. Progress to date (previous 3 months work) The communities for the study have been selected, and the project plan has been finalised. Current ongoing work (next 3 months) The data collection tools are currently being designed. Community researchers will be contracted. Fieldwork will be conducted. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.9 Maori Research Agenda Lead agency: Te Puni Kökiri

Background Te Puni Kōkiri is working to identify current information regarding family violence for Māori, and looking at culturally distinct models of prevention and intervention for Māori. It is expected that an agenda for research will emerge from this work. Progress to date (previous 3 months work) The scope of this project has been defined, and a stocktake of existing initiatives has been completed. There are three key outputs: Output One: A literature review intended to identify current information on Māori family violence; information gaps; inconsistencies; and themes within the literature on family violence and Māori. Output Two: A case study analysis of existing Māori designed, developed and delivered initiatives that address family violence. Output Three: A summative report that analyses output one and two and identifies research priorities to form a Māori Research Agenda. Current ongoing work (next 3 months) The contract for this work has been tendered, with a completion date of June 2008. Consultation with other agencies has been completed. An external Reference Group to review work is currently being established. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.10 Pacific Research Agenda Lead agency: Ministry of Pacific Island Affairs

Background The Ministry of Pacific Island Affairs is looking to develop a Pacific Research Strategy; its Family Violence Research Agenda will sit within this. Progress to date (previous 3 months work) The Ministry of Pacific Island Affairs has been in contact with the Taskforce’s Pacific Advisory Group (PAG). Current ongoing work (next 3 months) The Ministry of Pacific Island Affairs will consult with the PAG about what research on Pacific peoples and family violence is needed both now and in the future. Issues of capacity with regards to Pacific family violence research will also be discussed. A wider consultation will then be held with other relevant Pacific stakeholders in this area addressing the same matters. From here a report will be developed which will outline the issues associated with Pacific family violence research and culminate in the development of Pacific family violence research priority topics. Timing / Ongoing / Recommendations / Conclusions Status = on track. Variation to be submitted April 2008.

1.11 New Migrant and Refugee Research Agenda Lead agency: Ministry of Social Development

Progress to date (previous 3 months work) An annotated bibliography has been prepared and Is currently in draft format. This document covers national and international literature relating to family violence within the refugee and migrant communities. Current ongoing work (next 3 months) A synthesis of findings is currently being prepared summarising the literature covered in the annotated bibliography. A gap analysis will follow to examine how the existing literature covers the topics of interest for this project, and how they are covered in relation to the different areas that are included within family violence: - the nature of family violence in new migrant and refugee families - successful models of prevention - successful models of intervention. The synthesis of findings and gaps analysis will be discussed by an expert research group. A scoping paper outlining the completion of this project will be developed from that discussion. Timing / Ongoing / Recommendations / Conclusions Status = on track.

1.12 Elder Abuse and Neglect Lead agency: Ministry of Social Development

Background 1.12.2 and 1.12.3 The research agenda on Elder Abuse and Neglect (EAN) will be informed by the environmental scan (see 1.12.4 below). 1.12.4 Following a joint Age Concern NZ/MSD presentation to the Taskforce on a proposed national action plan/strategy on EAN, MSD and Age Concern have commenced an environmental scan with the view to preparing an ongoing national programme of action on EAN Policy. Progress to date (previous 3 months work) - Cross-MSD reference group for EAN Policy established. - MSD and Age Concern New Zealand agreed to jointly work on an environmental scan of EAN in New Zealand. Current ongoing work (next 3 months) - Draft environmental scan completed (Age Concern NZ and MSD) Timing / Ongoing / Recommendations / Conclusions Status = On track

1.13 Data on NGO Service Delivery Lead agency: Ministry of Social Development

Background The initiative to support a sustainable NGO social service sector (part of Pathway to Partnership) will roll-out a sustainable funding path for essential NGO services for families, children and young people. All essential Family Violence prevention services will be part of this initiative. As part of implementing this project, a data monitoring system that focuses on outcome measures will be developed in collaboration with the sector and implemented. This monitoring system will provide high quality data about services. Current ongoing work (next 3 months) A scoping study and a project plan outlining the implementation of the monitoring system is in development. Timing / Ongoing / Recommendations / Conclusions Status = on track.

### Changing Attitudes and Behaviour

2.1 Kia Puawai Lead agency: Ministry of Social Development

Background An early years budget package was developed in November 2007. It was designed to significantly strengthen our ability to identify and respond early to needs of all young children, especially the vulnerable. However, work on building an effective early years intervention system continues independent of the result of the Budget bid. Progress to date (previous 3 months work) The early years budget package was submitted to the Minister of Finance in December 2007. Current ongoing work (next 3 months) Further work is underway on improving the effectiveness of identification, assessment and referral for children under six years. The B4School pilot being progressed by the Ministry of Health will be in place by August 2008. Further confirmation of the scope of other initiatives will be possible after the Budget announcement in May 2008. Timing / Ongoing / Recommendations / Conclusions Status = some delay.

2.2 Improving Attachment Lead agency: Ministry of Health

Alert: Not commenced as initial scoping highlighted issues with site for pilot. New approach currently being considered by Ministry of Health.

2.3 Conduct Disorder / Sever Anti-Social Behaviour Lead agency: Ministry of Social Development

Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for 3-7 year old children. Progress to date (previous 3 months work) The Expert Advisory Group (EAG) had its first meeting on 14 November 2007. A sub-group of members met 30 January 2008 and on 5 March 2008. Members of the EAG are progressing the best practice report which is on track for completion in April 2008. Current ongoing work (next 3 months) Agencies are finishing a stock-take of services and the EAG will write a second report: Translating Evidence into Practice. Timing / Ongoing / Recommendations / Conclusions Status = on track

2.4 Curriculum development Lead agency: Ministry of Education

Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The New Zealand Curriculum The New Zealand Curriculum was launched on Tuesday 6 November 2007 and Te Marautanga o Aotearoa was launched on 15 November 2007. These foundation policy statements identify the knowledge, understanding, skills, and attitudes which all students must develop if they are to play a full part in the world in which they will live and work. A draft position paper, Kiwi Leadership for Principals, was launched on 13 Feb 2008 to begin the consultation process to develop a national Professional Leadership Strategy. Research shows that a principal’s job as an educational leader is pivotal to improving learning outcomes for all students. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people An increase in costs associated with delivering the student wellbeing contracts has resulted in a reduction in the number of teachers who will receive professional development on a whole-school, strength-based approach to wellbeing. In order to increase teachers’ access to this professional development training, a cascade model is being employed. This relies on lead teachers implementing changes strategies in their schools with the support of a facilitator. In order to reach teachers in non-participating schools, successful professional learning approaches identified through the evaluation of the student wellbeing contracts will be incorporated in the design and delivery of ongoing professional development contracts. A variation on this action is currently being considered by the Chair of the Taskforce. 2.4.3 Identifying and referring children affected by family violence to appropriate services The Ministry of Education (MoE) has provided professional development training to behaviour specialists on the assessment of risk. This will support behaviour specialists to identify a range of risks, including family violence. MoE have also been working with the Child, Youth and Family Service on improving education planning and support for children who are in care. It is likely that a high proportion of these children will have experienced family violence as well as other forms of child abuse and neglect.. Current ongoing work (next 3 months) 2.4.1 The New Zealand Curriculum The implementation plan for the New Zealand Curriculum is underway and is ongoing to ensure schools implement the Curriculum fully by 2010. MoE will lead ongoing discussions on what it means to be a leader in education. MoE plan to launch the draft Professional Leadership Strategy in August 2008. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people MoE have received an initial draft evaluation report of the student wellbeing contracts and will be responding to the evaluators regarding their findings. 2.4.3 Identifying and referring children affected by family violence MoE will identify options to advance discussions on the protocols for identifying and referring children affected by child sexual abuse. Timing / Ongoing / Recommendations / Conclusions Status = on track. Subject to Variation

2.5 Violence in the Media Lead agency: Families Commission

Background - Violence in the media and its impact on society generally was raised at the meeting with the Family Violence Ministerial Team and with members of the Mulri-Party Working Group on Family Violence, when the Taskforce’s First Report was presented in mid 2007. The first Programme of Action included an action to review how violence is portrayed in the media and in particular the 2004 Report on TV Violence in New Zealand, and advise on implications for the next Programme of Action. The Families Commission agreed to lead this work. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6- 11 years) as a vulnerable group and it was agreed that this group should be the initial focus of any public education work. A paper was presented to the Taskforce supporting public health approach and recommended that issues related to violence in the media should be seen in the context of the Taskforce’s overall programme of work (i.e. within violence prevention generally). Progress to date (previous 3 months work) Initial background and scoping work was carried out. Current ongoing work (next 3 months) An advisory group will be convened and options will be developed. Timing / Ongoing / Recommendations / Conclusions Status = on track.

2.6 The Campaign for Action on Family Violence Lead agency: Families Commission and the Ministry of Social Development

Background The Campaign for Action on Family Violence (the campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The campaign message ‘Family violence – It’s not OK’ has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The campaign is supported by a website, an 0800 Information Line and a Community Action Fund that provides financial support for community-led activities. Progress to date (previous 3 months work) The second phase of the campaign was launched in February 2008. This phase focuses on intimate partner violence and features TV advertisements of men talking about how they have chosen to stop being violent towards their families. The ads show the real life impact of family violence on children, partners, family and friends and have attracted widespread positive media coverage including TV1 News, Close Up, Good Morning Television, Women’s Weekly and the New Zealand Herald. The campaign website has recorded its highest number of visits since the launch of the second phase. In the week beginning 2 March 2008 there were 1534 visits to the site. Overall, there have been 30,463 visits to the website and 561,678 hits since the national launch in September 2007. The 0800 Information Line received a record number of calls just after the second phase ads started with operators handling 383 calls in the first week. The 0800 line operators have handled 4687 calls since the campaign was launched in September 2007. Two new resources have been developed to support the second phase of the campaign. A booklet for men reinforces the message that ‘Family Violence is not OK, but it is OK to ask for help’. The second booklet focuses on the impact family violence has on children and features children’s thoughts and feelings about the violence they have experienced. Current ongoing work (next 3 months) The second phase TV ads go off air at the end of March but will air for three more weeks before the end of the current financial year (dates to be confirmed). The campaign work is focused on extending stakeholder engagement, particularly targeting business, sport, popular culture and youth. A third round of the Community Action Fund will be launched in April and a series of regional hui are planned to bring together Community Action Fund recipients to share ideas. The campaign has also been listed as a finalist in the IPANZ Public Sector Excellence Awards. Winners will be announced in May 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track.

2.7 Family Violence Death Review Project Lead agency: Ministry of Health

Background In its First Report and Programme of Action, the Taskforce gave the Ministry of Health responsibility to design an ongoing process for reviewing all family violence-related deaths by June 2007. In response to this, the Ministry of Health established the cross-agency Family Violence Death Review Project in close collaboration with the Ministry of Social Development, the Ministry of Justice, the Police and other key government and non-government organisations. The Ministry of Health reported to the Taskforce on 30 June 2007 and recommended that a formal mechanism for an interagency, multidisciplinary family violence-related death review system be established under the New Zealand Public Health and Disability Act 2000 (the NZPHD Act). The family violence death review system proposed involves the establishment of a ministerial committee that is parallel to, but separate from, the current mortality review committees mandated under the NZPHD Act. The Taskforce agreed to the recommendations in the report. Progress to date (previous 3 months work) - An implementation manager was appointed in December 2007 to progress the establishment of the Family Violence Death Review Committee (FVDRC). - On 13 February 2008, the government considered a paper from the Minister of Health and noted that the Minister of Health intends to establish a Family Violence Death Review Committee under the New Zealand Public Health and Disability Act. - On 20 February 2008, the draft Terms of Reference for the FVDRC were released for external consultation. - On 20 March 2008, the Terms of Reference were sent to the Minister of Health for approval. Current ongoing work (next 3 months) - Recruitment is underway for a Senior Policy Analyst to provide Secretariat support to the Committee and a Business Analyst to investigate database options for the Committee. - The Ministry of Health intends to send out the call for nominations for the inaugural members of the Family Violence Death Review Committee on 26 March 2008 (subject to Ministerial approval). - The FVDR Project's steering and advisory groups will be reformed into one implementation advisory group, and will have its first meeting in May. - The Ministry plans to undertaken the Cabinet appointments process during May and June to appoint members to the Committee. - A written notice will be presented to the House of Representatives by the Minister of Health to establish the Committee (late June). Timing / Ongoing / Recommendations / Conclusions Status = on track.

### Ensuring Safety and Accountability

3.1 Family Violence Courts Lead agency: Judiciary / Ministry of Justice

Progress to date (previous 3 months work) The Chief District Court Judge has indicated that only two new Family Violence Courts will be implemented rather than 4-6, to allow time for the existing Family Violence Courts to bed in. Locations and dates for implementation are still to be confirmed. However the Chief District Court Judge has indicated that Palmerston North and Whangarei are likely locations for new Family Violence Courts to exist from July 2008. Current ongoing work (next 3 months) Once the location and implementation dates for the new Family Violence Courts are confirmed the Ministry of Justice will work closely with the Judiciary, court staff and key stakeholders (including Police Prosecutions, Community Probation and community agencies) at these locations to plan the implementation of the courts. The Ministry will also be looking to ensure that the staff and key stakeholders who will be working in those Family Violence Courts will receive specialist training on the dynamics of domestic violence and the philosophy of Family Violence Courts prior to the courts being implemented. A communications strategy will be developed in preparation for the launch of the new courts, in consultation with the Chief District Court Judge and the Minister for Courts. Timing / Ongoing / Recommendations / Conclusions Status = on track.

3.2 Family Violence Court Protocols Lead agency: Judiciary / Ministry of Justice

Progress to date (previous 3 months work) National Operating Guidelines for Family Violence Courts have been developed. These were unable to be released for consultation in December 2007 as planned, as the Ministry of Justice publicly tendered for a Family Violence Court Training Provider during this period and did not want to make detailed information unfairly available to some parties. The Guidelines have been approved by the Chief District Court Judge and, on his advice, have now been distributed to the Family Violence Court Judges for their consideration prior to broader consultation, which will occur by 30 March 2008. Current ongoing work (next 3 months) The Ministry has contracted an external provider to develop and deliver Domestic Violence Training to staff and key stakeholders at all Family Violence Courts by June 2008. Following approval the National Operating Guidelines will form the basis for this training. Successful training will result in successful implementation of protocols in all Family Violence Courts prior to this date. Timing / Ongoing / Recommendations / Conclusions Status = on track.

3.3 Social Services supporting Courts Lead agencies: Ministry of Justice / Ministry of Social Development

Progress to date (previous 3 months work) In January 2008 Taskforce approval was sought for a variation to this objective. The variation order seeks approval to change the actions in the project definition to the following. The objective has not been changed. - Introduction of Independent Victim Advocate / support person role in all Family Violence Courts; - Introduce specialist enhanced case management staff in all Family Violence Courts; and - Referral and funding for non-mandated stopping violence programme providers for offenders. The Variation is currently being considered by the Chair of the Taskforce. The previous deliverables and milestones did not align with the direction the Chief District Court Judge has set for the Family Violence Courts and were also not consistent with a 2008 Budget Bid for the Family Violence Courts. Current ongoing work (next 3 months) The Government has announced that it will move towards fully funding actions 1 and 3 of this objective from 2008/2009. The Ministries of Justice and Social Development will meet weekly from 3 March 2008 to discuss and agree the proposed approach to this work in light of this announcement. Timing / Ongoing / Recommendations / Conclusions Status = on track. Subject to Variation.

### Effective Support Services

4.1 Maori Service Workforce Development Lead agency: Ministry of Social Development

Progress to date (previous 3 months work) A collaborative approach is being used to develop appropriate resources for practitioners and facilitators of groups. All Mauri Ora training is well underway, numbers are currently higher than contracted and the courses are generating excellent feedback. Current ongoing work (next 3 months) There is a range of work underway specifically for practitioners including the development of a DVD with key leaders giving key messages. The purchase of existing resources ready for distribution is underway, facilitation training for practitioners working with groups is underway, as is the recruitment and training of supervisors for Mauri Ora practitioners. Timing / Ongoing / Recommendations / Conclusions Status = on track.

4.2 Pacific Service Workforce Development Lead agency: Ministry of Social Development

Background This work is now incorporated within the Pathway to Partnership (P2P) plan. P2P is a multi-year plan to build stronger, sustainable and more effective community-based social services for children, families and young people. As part of this work, MSD will be addressing providers’ ability to build workforce capability and capacity. Pacific service workforce development will be incorporated under this work-stream. A critical focus for the government is ensuring positive outcomes for children, young people and families by giving children the best start in life, realising youth potential, strengthening families and preventing family violence. Progress to date (previous 3 months work) On 12 February 2008, the Government announced an additional funding package for the P2P plan worth $446 million, to be phased in over the next four years. The aim of the plan is to improve the quality and sustainability of NGO social services in order to make a real difference in the lives of children, families and young people. A steering group for the P2P plan has overseen the development of P2P over the last year. A representative from the Ministry of Social Development’s Pacific Advisory Group is on this steering group. Current ongoing work (next 3 months) The Pacific Advisory Group is due to meet with MSD in April 2008 to discuss P2P. Timing / Ongoing / Recommendations / Conclusions Status = some delay.

4.3 Service Demand Data Lead agency: Ministry of Social Development

Background Monitoring systems were developed to measure the initial impact in service demand associated with the Campaign for Action on Family Violence. These monitoring systems included data from the 0800 number, CYF and Police. The quantitative measures included in these monitors will be repeated. Qualitative data collected from the NGO sector in selected communities will compliment the quantitative monitors providing data directly from the NGO sector. The qualitative data collection will focus on the contribution that the Campaign for Action on Family Violence has had on any change in service demand experienced by the NGO sector since the commencement of the Campaign. Progress to date (previous 3 months work) Monitoring systems developed in latter part of 2007. Current ongoing work (next 3 months) Timing / Ongoing / Recommendations / Conclusions Status = on track.

## Detailed Milestone Updates

This section provides short-form updates on objectives, and actions and milestones within each objective.

### Leadership

| 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Taskforce Secretariat / All Taskforce agencies |  |
| Project Manager |  |  |  | Carra Hamon |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: - Stewardship of the Ongoing Programme of Action work programme - Stewardship of children specific work programme - Stewardship of all other work programme |  |  |  |  |  |
| Deadline |  | Ongoing |  |  |  |
| Purpose |  |  |  |  |  |
| To successfully monitor and ensure implementation of the Ongoing Programme of Action. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.1.1 | Stocktake of First POA actions |  | Jan 2008 |  | Table completed. |
| 1.1.2 | Draft monitoring report with officials’ input |  | 6 Mar |  | Monitoring reports will focus on OPOA, with regular audits of work from the first POA. |
| 1.1.3 | First ongoing monitoring report for 2008 to Taskforce. |  | 20 Mar |  | Contacted officials for update 12 Feb 2008. This report will go to 2 April meeting. |
| 1.1.4 | Officials contacted for updates for June Taskforce meeting monitoring report |  | 5 April |  | On track |

| 1.1a MAPPING OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | NGOs |  |
| Contributors |  |  |  |  |  |
| Project Manager |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Actions include: - Ongoing Programme of Action mapped to its outcome. |  |  |  |  |  |
| Deadline |  | Alert |  |  |  |
| Purpose |  |  |  |  |  |
| Alert |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
|  | Alert |  |  |  |  |

| 1.2 MAORI PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agencies |  |  | Maori Reference Group Ministry of Social Development |  |  |
| Contributors |  |  | Te Puni Kokiri, NGOs |  |  |
| Project Manager |  |  | Ann Dysart (MSD) |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| A Programme of Action focused on eliminating violence in Maori whänau is developed. Actions include: - Developing a Maori Programme of Action - Ensuring the leadership and ownership of the actions at all levels of Te Ao Maori |  |  |  |  |  |
| Deadline |  | June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To develop a process and plan that engages all areas of Te Ao Maori in owning and addressing the issues of Family Violence and Child abuse. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 1.2.1 | Draft Maori Communication Strategy |  |  | Jan 08 | Developed, will be used for Summit |
| 1.2.2 | Maori Whanau Summit |  |  | 3 & 4 April 08 | Maori Whanau Summit - 3-4 April |
| 1.2.3 | Local regional hui with Maori family providers and practitioners |  |  | April / May 08 | Regional Hui dates TBC |
| 1.2.4 | Launch Maori Programme of Action. Work towards establishing action plan for 08/09 and priorities for next five years |  |  | June 08 | On track |

| 1.3 PACIFIC PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Pacific Advisory Group Ministry of Social Development |  |
| Contributors |  |  |  | Ministry of Pacific Island Affairs, NGOs |  |
| Project Manager |  |  |  | Liz Tanielu (MSD) |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: - Develop a Pacific Programme of Action |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| To articulate the status of Family Violence as it impacts on Pacific People and outline specific action to address it. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.3.1 | Draft Pacific POA |  | Jan 08 |  | Draft developed, circulated to PAG. |
| 1.3.2 | Stakeholder Meetings for input into POA |  | March 08 |  | Consultation begun. |
| 1.3.3 | Final POA |  | June 08 |  | On track. |

| 1.4 CHILD ABUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Office of the Children’s Commissioner |  |
| Contributors |  |  |  | MSD, NGOs, Justice, Health, Education, Police |  |
| Project Sponsor |  |  |  | Dr Cindy Kiro |  |
| Project Manager |  |  |  | Jenni Nana (MSD) |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| A long term plan is developed for government’s work on addressing child abuse (including child sexual abuse) within families. Actions include: - Assess current work on prevention and reduction of child sexual abuse - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Include children with disabilities within this work - Plan future work - Ensure ongoing communications between Taskforce and Taskforce for Action on Sexual Violence |  |  |  |  |  |
| Deadline |  | 30 June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| Child abuse in New Zealand has been difficult to quantify and fully understand. General consensus holds that child abuse occurs predominantly within families. This work will develop an integrated, cross government approach to work on child abuse which has attached to it a growing evidence and knowledge base. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.4.1 | Meeting with Sponsor on project plan |  | 4 Oct 2007 |  | This meeting was held on 4 October, at which time it was discussed that the project brief has been expanded due to agreement of the Taskforce at the 3 October meeting. |
| 1.4.2 | Report progress to Taskforce |  | 6 Dec 2007 |  | An early draft of the paper on child sexual abuse was presented to the Taskforce and circulated to other agencies for comment. |
| 1.4.3 | Final paper on child sexual abuse |  | Feb 2008 |  | A final draft of the paper, incorporating the comments of other agencies, is ready to be circulated to agencies for final comments and forwarded to the Taskforce. |
| 1.4.4 | Stocktake paper on child abuse (excluding sexual abuse) Collating and reviewing current research Summary of service response |  | April 2008 |  | Similar to the early paper on child sexual abuse, a stocktake on our current response to child abuse will be developed. |
| 1.4.5 | Draft work programme developed |  | June 2008 |  | Drawing together the already agreed actions on child sexual abuse with the proposed actions for the remaining types of child abuse, one integrated work programme will be developed and agreed by the Taskforce. |

| 1.5a FAMILY VIOLENCE FREE WORKPLACES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | ACC, Police, NGOs |  |
| Project Manager |  |  |  | David Dick |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Family Violence -Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector |  |  |  |  |  |
| Deadline |  | May 2012 |  |  |  |
| Purpose |  |  |  |  |  |
| Family Violence Free Workplaces means staff in those workplaces is aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Free Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.5a.1 | Human Resources Plan |  | Oct 2007 |  | Complete. Presented to the Human Resource Governance Committees for Policy and Service Delivery business areas. |
| 1.5a.2 | Policy development |  | Oct 2007 |  | Draft completed – to be progressed through approval processes |
| 1.5a.3 | Establish internal steering group to oversee Family Violence initiatives |  | Dec 07 |  | Held up due to change of DCE in Policy Group. |
| 1.5a.4 | Manager guidelines developed to support policy. Published on MSD intranet site |  | Dec 2007 |  | Draft guidelines developed and to be progressed through approval process |
| 1.5a.5 | Raising Awareness of Family Violence - National Office information sessions - Regional info sessions |  | Sep 2007 Mar 2008 |  | Completed. Information sessions scheduled for National Office staff. Developing information session package. To liaise with ACC to explore combined sessions. |
| 1.5a.6 | Providing accessible information and resources - Information and links placed on intranet site - Provide informational resources for workplaces – such as posters, booklets, toolkits |  | Sep 2007 Dec 2007 |  | Completed. FV Campaign logo on front page of intranet as a link. Will use resources from the FV Campaign. Posters distributed to business units. |
| 1.5a.7 | Tools and resources - address concerns about Family Violence counselling services available through current EAP provider - Explore the development of web-based family violence resources for the workplace |  | Oct 2007 2009 |  | Completed. Provided information to feed into RFP process for new Employee Assistance Program provider. Still in earlier exploration stages. Subject to potential joint development between Family and Community Services and PVH and funding. |
| 1.5a.8 | Training - In-depth family violence training for line HR staff and HR consultancy. - Deliver additional training programmes for key support people and all staff as required |  | Sep 2007 |  | Completed. PVH (Preventing Violence in the Home) delivered two-half day training sessions for HR staff. To be programmed subject to demand. |
| 1.5a.9 | Peer support framework developed - approval - developed - pilot - track and assess roll-out to other areas. |  | Dec 2008 |  | Complete. Peer support programme launched in Dec 2007 to provide in-house support on family violence and information services. A review meeting will be held in June 2008. CYF considering as part of broader peer support framework for staff |

| 1.5b FAMILY VIOLENCE FREE WORKPLACES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  |  | Accident Compensation Corporation |  |
| Contributors |  |  |  |  | MSD, Police, NGOs |  |
| Project Manager |  |  |  |  | Danielle George |  |
| First Programme of Action reference |  |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |  |
| Family Violence -Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector |  |  |  |  |  |  |
| Deadline |  |  | December 2008 |  |  |  |
| Purpose |  |  |  |  |  |  |
| Family Violence Free Workplaces means staff in those workplaces is aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |  |
| Key Milestones |  |  |  | Date |  | Description of Progress |
| 1.5b.1 |  | Family Violence staff resources |  | 14/09/2007 |  | Intranet site published and resources available. |
| 1.5b.2 |  | Release of Family Violence Policy |  | 15/11/2007 |  | Policy currently being updated |
| 1.5b.3 |  | HR Co-ordinator skills development |  | 31/12/2007 |  | Working with PVH to adapt MSD tools for ACC |
| 1.5b.4 |  | Training programmes and managers guides |  | 31/03/2008 |  | Initial half day pilot run for HR staff by PVH. Training did not meet the needs of the organisation and alternative supplier or modifications to PVH module under investigation. Still on track for 31 March completion |
| 1.5b.5 |  | Policy and guideline refresh |  | 31/03/2008 |  | Refresh launch of policy and guidelines, Family Violence Support also launched as part of ACC’s Staff Wellbeing programme in February 2008 |
| 1.5b.6 | FVFW established across ACC |  |  | 31/12/2008 |  | On track for fully embedded across ACC by end of 2008 |

| 1.5c FAMILY VIOLENCE FREE WORKPLACES |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | New Zealand Police |  |
| Contributors |  |  | MSD, ACC, NGOs |  |
| Project Manager |  |  | Carol Train |  |
| First Programme of Action reference |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |
| Family Violence -Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector. |  |  |  |  |
| Deadline |  | May 2012 |  |  |
| Purpose |  |  |  |  |
| Family Violence Free Workplaces will raise the awareness of staff in the Police about family violence and provide support where appropriate. Police staff may be victims, observers or perpetrators of family violence. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 1.5c.1 | Policy developed and agreed |  | Dec 2008 | On track, meeting with MSD as have progressed this project further. |
| 1.5c.2 | Training and resource developed |  | Dec 2009 | On track |
| 1.5c.3 | Communications package completed |  | Jan 2010 | On track |
| 1.5c.4 | Training Delivered in all Districts |  | Dec 2010 | On track |
| 1.5c.5 | Family Violence Free Workplaces established in Police |  |  | On track |
| 1.5c.6 | Evaluation of Police model |  | Dec 2011 | On track |
| 1.5c.7 | Finalise Blueprint for implementing Family Violence Free Workplaces in public, private and non-government sectors |  | May 2012 | On track |

| 1.6 IWI LED CRIME PREVENTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | New Zealand Police |  |
| Contributors |  |  |  | Iwi, NGOs, Te Puni Kokiri |  |
| Project Manager |  |  |  | Wally Haumaha |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Iwi led crime prevention plans which have a focus on the prevention of family violence Actions include: - Provide support to iwi to develop plans - Iwi led crime prevention strategies developed in accordance with each iwi identified needs, values and timeframes |  |  |  |  |  |
| Deadline |  | This is an iterative and evolving process that is being driven by iwi. Precise deadlines are neither available, nor appropriate at this stage. |  |  |  |
| Purpose |  |  |  |  |  |
| In absolute numbers, more Maori churn through the criminal justice system every year than graduate from University. A new framework for action is being developed by Maori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Maori criminal justice outcomes. They are led by iwi, with assistance from officials. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.6.1 | Iwi to populate their crime prevention plan templates |  | No deadline |  | On track |
| 1.6.2 | Officials to condense those templates into A3 summaries |  | No deadline |  | Pending |
| 1.6.3 | Summaries to be presented back to iwi for confirmation |  | No deadline |  | Pending |
| 1.6.4 | Ministerial briefing paper to Ministers of Justice, Police and Maori Affairs |  | March 2008 |  | On track |

| 1.7 FAMILY VIOLENCE CLEARINGHOUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | Families Commission, NGOs |  |
| Project Manager |  |  |  | Jeff Sheerin |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| The Family Violence Clearinghouse (FVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: - Develop a model and systems which optimise the operations of the FVC |  |  |  |  |  |
| Deadline |  | June 2009 |  |  |  |
| Purpose |  |  |  |  |  |
| To review Family Violence Clearing House activities and services and develop a strategy for moving forward. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.7.1 | Negotiate contract with Canterbury University |  | 30 Jan 2008 |  | Negotiations commenced. Considering the option to extend the length of the contract until a new approach is implemented |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy |  | 30 April 2008 |  | * subject to human resource availability |
| 1.7.3 | Develop 2-5 year strategy |  | 30 June 2008 |  | * subject to human resource availability |
| 1.7.4 | Develop project plan and secure funding |  | 31 June 2008 |  | * subject to human resource availability |
| 1.7.4 | Implement new clearinghouse website and service |  | 31 Dec 2008 |  | * subject to human resource availability |

| 1.8 CASE STUDIES CHARACTERISING GOOD PRACTICE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs, Justice, Police |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Case studies characterising good practice in service aimed at eliminating family violence are developed and made publicly available. Actions include: - Scope and identify existing good practice models - Record the characteristics of their success - Index and deposit in Family Violence Clearinghouse. |  |  |  |  |  |
| Deadline |  | October 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To describe and generalise good practice principles as they apply to family violence prevention. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.8.1 | Identification of case study subjects |  | April 2008 |  | Generating options for case study development |
| 1.8.2 | Draft case studies |  | Sept 2008 |  | On track |
| 1.8.3 | Final case studies |  | Oct 2008 |  | On track |

| 1.9 MAORI RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Te Puni Kokiri |  |
| Contributors |  |  |  | MRG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Te Atarangi Whiu |  |
| First Programme of Action reference |  |  |  | New initiative |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Recommend further action. |  |  |  |  |  |
| Deadline |  | 30 June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To increase the evidence base by providing case studies of a minimum of three Maori designed, developed and delivered programmes. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.9.1 | Progress Report |  | 31 Jan 08 |  | Scope of project defined. Three key outputs. |
| 1.9.2 | Final Report |  | 30 Jun 08 |  | On track |

| 1.10 PACIFIC RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Pacific Island Affairs |  |
| Contributors |  |  |  | PAG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Su’a Thomsen |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) A Variation is about to be submitted to the Chair of the Taskforce. Content may differ in this objective from previous reporting. |  |  |  |  |  |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: - Finalise project plan - Consultation with Pacific Advisory Group - Consultation with other Pacific stakeholders - Development of report including identification of Pacific Family Violence Research priorities |  |  |  |  |  |
| Deadline |  | Final deadline to be confirmed |  |  |  |
| Purpose |  |  |  |  |  |
| To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.10.1 | Finalise project plan |  | April 2008 |  | Project plan in development, currently holding stakeholder discussions |
| 1.10.2 | Consult with Pacific Advisory Group |  | May 2008 |  | Not yet commenced |
| 1.10.3 | Consult with other Pacific stakeholders |  | June 2008 |  | Not yet commenced |
| 1.10.4 | Completion of report |  | August 2008 |  | Not yet commenced |

| 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Recommend further action |  |  |  |  |  |
| Deadline |  | To be provided after the scoping phase |  |  |  |
| Purpose |  |  |  |  |  |
| A statement of purpose will be developed in the scoping phase. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.11.1 | Synthesis of literature |  | April 2008 |  | Annotated bibliography drafted. |
| 1.11.2 | Scoping paper |  | June 2008 |  | On track |

| 1.12 ELDER ABUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Cilla Corlett |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions |  |  |  |  |  |
| Improve our understanding of the nature of elder abuse and successful models of prevention and intervention. Actions include: - Review existing literature - Develop a research agenda - Link to the Taskforce strategic research agenda for family violence prevention - Recommend further action |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| Expected Outcome: Improved decision-making about viable programme and service delivery to eliminate elder abuse and neglect within the family setting. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.12.1 | Review existing literature |  | Jan 2006 |  | Literature Review completed by CSRE: refer http://www.msd.govt.nz/work-areas/social-research/older-people/elder-abuse-neglect.html |
| 1.12.2 | Develop a research agenda |  | 30 June 2008 Sept 2006 Dec 2007 2007 2007 |  | On track. MSD is currently working with Age Concern and the Families Commission in drafting a cross-sectoral national Action Plan for elder abuse and neglect. As part of the Action Plan a Research Strategy for EAN is also being developed. In September 2006, the Families Commission and Age Concern NZ hosted a workshop to identify key research priorities for EAN prevention. Potential topics for research on EAN were identified at the workshop and will help to inform the Research Strategy. In the Taskforce’s First Report (July 2006), it endorsed the Families Commission’s three-year research work programme to improve our understanding of the nature of family violence and appropriate prevention strategies. Accordingly, the Families Commission commissioned research exploring the risk and protective factors associated with elder abuse and neglect. The research report was released on 26 February 2008. Age Concern New Zealand has released a summary of the findings from the study Elder Neglect: an analysis of cases referred to Age Concern New Zealand during 2002-2006, for the Enhancing Wellbeing in an Ageing Society (EWAS) research programme being conducted by The Family Centre Social Policy Research Unit and The Population Studies Centre, University of Waikato. In August 2007, the Ministry of Health published Family Violence Intervention Guidelines: Elder Abuse and Neglect for health care providers to use when identifying and responding to elder abuse. This publication is a valuable addition to the knowledge base - particularly as it is written for the New Zealand context. |
| 1.12.3 | Link to the Taskforce strategic research agenda for family violence prevention |  | Ongoing |  | Although the proposed programme of action on EAN will encompass all forms of elder abuse and neglect across all settings, not just within families, strong links will be made between the EAN research strategy and the Taskforce strategic research agenda for family violence prevention. |
| 1.12.4 | Recommend further action |  |  |  | Not defined as yet |

| 1.13 DATA ON NGO SERVICE DELIVERY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | NGOs, ACC, Justice, Police, Health |  |  |
| Project Manager |  |  | Dorothy Adams |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions |  |  |  |  |  |
| High quality data available about services delivered by, and on the demand for NGO and agency family violence services. Actions include: - Develop systematic and accurate data on services |  |  |  |  |  |
| Deadline |  | To be confirmed after scoping work completed |  |  |  |
| Purpose |  |  |  |  |  |
| A purpose statement will be derived from the scoping study. This work is aligned with the “Supporting a Sustainable NGO Social Service Sector” initiative. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 1.13.1 | Scoping study and project plan |  |  | July 2008 | On track |
|  | No further milestones provided |  |  |  |  |

### Changing Attitudes and Behaviour

| 2.1 KIA PUAWAI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | All Taskforce members |  |
| Project Manager |  |  |  | Alun Hughes |  |
| First Programme of Action reference |  |  |  | Not in First Programme of Action |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Kia Puawai supported in its implementation by the Taskforce. Taskforce supports initiatives such as: - increasing coverage of intensive home visiting - providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years - developing an integrated identification, assessment and referral system for young children - expanding Early Years hubs and teen parent co-ordinators initiatives - key workers to support at-risk families - expanding Social Workers in Schools. |  |  |  |  |  |
| Deadline |  | Ongoing |  |  |  |
| Purpose |  |  |  |  |  |
| This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as yond adults capable of developing healthy, respectful and violence free relationships throughout their lives. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.1.1 | Early years budget package developed |  | Mid Nov 07 |  | Completed. Submitted December 2007. |
| 2.1.2 | Progress report delivered to Ministers on results of evaluations of pilot programmes to improve outcomes for children and their families. |  | Nov 08 |  | Not yet commenced, awaiting result of 2.1.1. |
| 2.1.3 | B4School check pilot in place |  | Aug 08 |  | Work underway. |

| 2.2 IMPROVING ATTACHMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Health / Auckland District Health Board |  |
| Contributors |  |  | MSD, ACC, Education, NGOs |  |
| Project Manager |  |  | Pat Tuohy / Carol Stott |  |
| First Programme of Action reference |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |
| Promote and improve attachment between new-born babies and parents and care givers. Actions include: - Progress a pilot - See how well it works - Report - Draw on key findings from parent support and development programmes already focused on supporting attachment between young children and parents and caregivers |  |  |  |  |
| Deadline |  | July 2009 |  |  |
| Purpose |  |  |  |  |
| Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be provided through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 2.2.1 | Inclusion of an additional visit in the Well Child Framework for first time parents especially for fathers and male partners |  | July 2009 | Not commenced |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties in revised Well Child Framework |  | July 2009 | Not commenced |
| 2.2.3 | Training for Well Child Providers to promote secure infant- parent attachment |  | July 2009 | Not commenced |
| 2.2.4 | Establishment of a pilot in the Auckland District Health Board area to prevent Shaken Baby Syndrome (head injuries to babies caused by violent shaking). |  | TBC | Delayed. The Auckland DHB has decided not to proceed with this pilot as it was not considered a funding priority. The reason being is that the majority of babies admitted to Starship Hospital with head injuries as a result of Shaken Baby Syndrome are from outside the Auckland DHB’s area. The Ministry has been approached to fund a regional pilot across the three Auckland DHBs and is currently considering whether funding could be made available for this initiative. |

| 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | Education, Health, Justice, NGOs, OCC |  |  |
| Project Manager |  |  | Alun Hughes |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Ensure comprehensive behavioural interventions for children aged 3 – 7 years with conduct disorder/severe antisocial behaviour and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behaviours services already provided by the Ministry of Education. Taskforce supports the four action areas in the Inter-Agency Plan: - leadership, co-ordination, monitoring and evaluation - transition existing service provision to evidence-based, best-practice interventions - establish an intensive, comprehensive behavioural service for 3 -7 year olds - build a shared infrastructure for the delivery of specialist behavioural services. |  |  |  |  |  |
| Deadline |  | 2012 |  |  |  |
| Purpose |  |  |  |  |  |
| Developing and delivering a suite of services for the 5% of primary and intermediate aged children who have conduct disorder/severe anti-social behaviour will reduce the prevalence of children at intermediate schools with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are expected to result in a reduction in severe cases of family violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.3.1 | Establish experts advisory group |  |  | Mid Nov 2007 | Completed |
| 2.3.2 | Best practice report completed |  |  | Apr 2008 | On track |
| 2.3.3 | Agency service reviews completed |  |  | Dec 2008 | On track |

| 2.4 CURRICULUM DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Education |  |  |
| Contributors |  |  | MSD (MYD), Health, TPK, MPIA, OCC, NGOs |  |  |
| Project Manager |  |  | Sue van Daatselaar |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) A Variation is currently being considered by the Chair of the Taskforce. Content may differ in this objective from previous reporting. |  |  |  |  |  |
| Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: - Provide support to enable schools to develop their programmes within the New Zealand curriculum to suit the diverse learning needs of their community - Strengthen whole-school, strengths-based approaches that promote resilience and confidence in young people and those adults who support them - Seek opportunities to identify and respond to children who are affected by family violence. |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own well-being and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whanau, and other agencies to ensure these students are appropriately supported. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes within the New Zealand curriculum (NZC) to suit the diverse learning needs of their community. - Release final curriculum and supporting resources for schools to support the implementation of the curriculum - Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families/whanau in focusing on student achievement and educational outcomes based on the NZC. |  |  | Dec 07 & ongoing June 08 & ongoing | Complete. NZ Curriculum launched 6 Nov 2007, Te Marautanga o Aotearoa launched 15 Nov 2007. Draft position paper, Kiwi Leadership for Principals, launched 13 Feb 2008 to begin consultation on development of a national Professional Leadership strategy |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. - Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student well being / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery and community consultation and partnerships. - Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. |  |  | June 08 & ongoing | Subject to variation. An increase in costs associated with delivering the student wellbeing contracts from the original 2005 contracts reduced the number of teachers that can receive this professional development |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. - Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. - Develop and implement an action plan to ensure that children and young people identified while at school as affected by family violence receive the support they need (in conjunction with obj 1.4 Child Abuse) |  |  | June 08 Sept 08 & ongoing | The Ministry of Education has provided professional development training to behaviour specialists on the assessment of risk Working with Child, Youth and Family Service on improving education planning and support for children in care |

| 2.5 VIOLENCE IN THE MEDIA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Radha Balakrishnan |  |
| First Programme of Action reference |  |  |  | Action 23 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Create awareness of impact of violence in the media on children aged between 6 to 11 years. Actions include: - Scope an evidence-based public education and awareness programme aimed at parents - Scope financial implications - Develop an implementation plan. |  |  |  |  |  |
| Deadline |  | February 2009 |  |  |  |
| Purpose |  |  |  |  |  |
| To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.5.1 | Convene Advisory Group |  | Aug 2008 |  | On track |
| 2.5.2 | Develop plan |  | Oct 2008 |  | Not commenced |
| 2.5.3 | Draft Report circulated for comment |  | Dec 2008 |  | Not commenced |
| 2.5.4 | Report to the Taskforce |  | Feb 2009 |  | Not commenced |

| 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Families Commission / MSD |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Nick Farland / Gael Surgenor |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Continue the Campaign for Action on Family Violence through: - An advertising campaign - Resource development and distribution - Community Action Fund projects |  |  |  |  |  |
| Deadline |  | 30 June 2008 (ongoing to 2010) |  |  |  |
| Purpose |  |  |  |  |  |
| This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes and towards family violence and motivators and barriers to behaviour change. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.6.1 | Run a television advertising campaign addressing attitudes to family violence and intimate partners violence during 2007/08 |  | 30 June 2008 |  | On track The first set of television adverts has been aired. The second set of four advertisements, focussing on stories of positive change is currently on air and will run to the end of March |
| 2.6.2 | Develop a range of resources to support the messages of the television campaign during 2007/08 |  | 30 June 2008 |  | On track Existing resources (the ‘Are you OK’ booklet, Community Action Tool Kit, Resources for journalists and web-based information and support) continue to be distributed. New resources, including a series of posters, balloons, Pacific posters, banners, and a small wallet sized booklet, have now been developed and are also being distributed. Two new booklets that were produced to support phase two of the campaign, one focusing on the impacts of violence on children and the other focusing on connecting with men around issues of violence, have been very popular. The 0800 telephone line continues to provide information and support. The number of male callers to the line remains high at 45%. There has been an increased number of email enquiries to the Campaign team via the website since the second phase of advertising started. |
| 2.6.3 | Support local projects to support change at a local level by administering at least one round of the Community Action Fund |  | 15 June 2008 |  | Achieved Two rounds of the Community Action Fund have been completed and a total of 62 community initiatives have been funded. |
| 2.6.4 | Measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign |  | 30 June 2008 |  | On track CSRE has released reach and retention survey results on the effectiveness of the Family Violence It’s not OK campaign. The results show that the campaign has been extremely effective to date in engaging with all New Zealanders (including Maori and Pacific communities, men and women). Very high numbers of people are recalling the adverts (89%), and a significant number of people are changing the way they think and act as a result. |

| 2.7 FAMILY VIOLENCE DEATH REVIEW PROJECT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Health |  |
| Contributors |  |  |  | MSD, Justice, Police, NGOs |  |
| Project Manager |  |  |  | Tanith Robb |  |
| First Programme of Action reference |  |  |  | Action 42 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| To establish the Family Violence Death Review Committee |  |  |  |  |  |
| Deadline |  | 31 June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| The Family Violence Death Review Committee is being established to understand why family violence deaths occur and to enable changes to systems and practices that may contribute to the prevention of future deaths. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.7.1 | Undertake consultation on draft Terms of Reference |  | 29/02/08 |  | Completed |
| 2.7.2 | Finalise Terms of Reference and seek Ministerial sign-off |  | 31/03/08 |  | Completed |
| 2.7.3 | Seek nominations for the inaugural members of the Committee |  | 31/03/08 |  | On track (subject to Ministerial sign-off) |
| 2.7.4 | Undertake Cabinet appointments process |  | 20/06/08 |  | On track |
| 2.7.4 | Appoint members to the Committee |  | 31/06/08 |  | On track |
| 2.7.4 | Establish Committee |  | 31/06/08 |  | On track |

### Ensuring Safety and Accountability

| 3.1 FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs |  |
| Taskforce Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Maria McDonald |  |
| First Programme of Action reference |  |  |  | Action 56 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| 2 new Family Violence Courts established. Actions include: - Project planning - Identification of locations - Stakeholder consultation - Implementation. |  |  |  |  |  |
| Deadline |  | June 08 |  |  |  |
| Purpose |  |  |  |  |  |
| To ensure all parties are prepared ahead of the implementation to support new Family Violence Courts being established. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.1.1 | Project planning for implementation and establishment of 2 new Family Violence Courts |  | 30 June 2008 |  | On track. High level project planning has been completed and the Ministry is awaiting direction from the Chief District Court Judge on the court locations and dates for implementation. More detailed project planning will be developed once the Judge has decided the locations. |
| 3.1.2 | Identification of locations |  | TBC |  | Subject to the Chief District Court Judge confirming the new Family Violence Court locations, the Ministry will complete a communications strategy in consultation with the Chief District Court Judge and the Minister for Courts. |
| 3.1.3 | Stakeholder consultation |  | TBC |  | Awaiting decisions as above |
| 3.1.4 | Communications strategy |  | TBC |  | Awaiting decisions as above |
| 3.1.5 | Implementation of 2 new Family Violence Courts |  | 30 June 2008 |  | Judiciary responsible |

| 3.2 PROTOCOLS FOR FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs. |  |
| Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Maria McDonald / Hayley Corbett |  |
| First Programme of Action reference |  |  |  | Action 57, 58 |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| A national protocol for improving how Family Violence courts are established and run. Actions include: - Develop protocols - stakeholder consultation - Implementation. |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| The purpose of this protocol will be to: - Outline the requirements of key staff involved in Family Violence Courts - Outline key areas of best practice to ensure there is consistency across all Family Violence Courts. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.2.1 | Development of Operating Guidelines to ensure consistency across all Family Violence Courts |  | 21 Dec 2007 |  | Complete mid Nov - Draft Operating Guidelines have been developed for internal consultation. |
| 3.2.2 | Consultation and communication of Operating Guidelines with key staff and stakeholders |  | 21 Dec 2007 |  | Broader consultation will occur by 30 March 08 following consideration by the Family Violence Court Judges. |
| 3.2.3 | Approval and distribution of Operating Guidelines across all Family Violence Courts |  | Completed by 30 June 08 |  | On track |
| 3.2.4 | Communications strategy |  | End of June 08 |  | On track |

| 3.3 SOCIAL SERVICES SUPPORTING COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development / Ministry of Justice |  |
| Contributors |  |  |  | Police, MWA, NGOs, ACC |  |
| Project Manager |  |  |  | Alun Hughes / Justine Cornwall |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) A Variation is currently being considered by the Chair of the Taskforce. Content may differ in this objective from previous reporting. |  |  |  |  |  |
| A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: - Introduction of Independent Victim Advocate / support person role in all Family Violence Courts - Introduce specialist enhanced case management staff in all Family Violence Courts - Referral and funding for non-mandated stopping violence programme providers for offenders. |  |  |  |  |  |
| Deadline |  | 2009 |  |  |  |
| Purpose |  |  |  |  |  |
| A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.3.1 | Draft project plan with on-going milestones and agency roles prepared |  | 5 Dec 2007 |  | MoJ and MSD met on 18 February 2008 to arrange weekly meetings and progress the project plan. |
| 3.3.2 | Introduction of Independent Victim Advocate / support person role in all Family Violence Courts |  | To April 2009 |  | Government announced funding for this role in February 2008. Development of the role is underway. |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts |  | April 2008 |  | MoJ is currently assessing other funding streams to fund this initiative. |
| 3.3.4 | Referral and funding for non-mandated stopping violence programme providers for offenders |  | July 2008 |  | Government announced funding for this role in February 2008. MoJ to determine and establish internal funding streams and processes for this initiative. |

### Effective Support Services

| 4.1 MAORI SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | TPK, NGOs, Education |  |  |
| Project Manager |  |  | Ann Dysart |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Maori Service Workforce Development. Actions include: - 60 Mäori trained to work with the Mauriora framework. |  |  |  |  |  |
| Deadline |  | June 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| This proposal will allow for continued investment in the training and support of practitioners who work with Mäori whänau/communities where there is violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.1.1 | Maori Reference group established to advise the Taskforce for Action on Violence within Families on the implementation of this and other initiatives aimed at reducing violence in Mäori whänau and communities. |  |  | 1 July 07 | Complete. There have been three meetings held since July 2007. Meetings have been ongoing at least every two months. |
| 4.1.2 | Contract in place with Te Korowai Aroha. |  |  | 30 Aug 07 | Complete - ongoing reporting. Contract signed, relationship in place, monitoring and reporting underway to schedule. |
| 4.1.3 | Funding and support for trained practitioners working to prevent violence in Mäori whänau and communities, including assisting Mauri Ora practitioners to meet annual licensing and supervision requirements; |  |  | Jun 08 | An analysis is underway of the needs of practitioners in this field. It is expected that some of the identified training will be available early in December |
| 4.1.4 | Delivery of training (including Mauri Ora training) to a minimum of 60 practitioners in 2007/08. The trainees will be Maori Practitioners who are working in both Maori and non-Maori provider organisations; |  |  | June 08 | Training is underway for practitioners in Tamaki Makaurau, Manawatu, Taranaki and the Central plateau. Training is also underway in the South Island |
| 4.1.5 | Contract in place for the development of supervision systems and the training of appropriate supervisors for the graduates of the programme. |  |  | Jan 08 | Complete. Contract in place. Development of supervision systems underway, appropriate people currently being selected for training. |

| 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | MPIA, NGOs, Education |  |  |
| Project Manager |  |  | Richard Joblin |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Pacific Service Workforce Development. Actions include: - Preparation of a strategy to guide workforce training and development in family violence services for Pacific families. |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| This work plans to increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.2.1 | Project plan developed under Pathway to Partnership to address building provider workforce capability and capacity. This will include the development of the Pacific workforce. |  |  | June 2008 | This work is now incorporated under the Pathway to Partnership plan, the project plan for which is currently being clarified and confirmed. |

| 4.3 SERVICE DEMAND DATA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | NGOs, Justice, Health, ACC, Police |  |  |
| Project Manager |  |  | Dorothy Adams |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Monitor increases in demand for family violence services resulting from the Campaign to create sustainable responses to increased demand. Actions include: - Develop monitoring framework - Create a system response mechanism. |  |  |  |  |  |
| Deadline |  | October 2008 |  |  |  |
| Purpose |  |  |  |  |  |
| To identify changes in service demand associated with the roll out of The Campaign for Action on Family Violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.3.1 | Measure initial service impact after the launch of the mass media campaign. |  |  | October 2007 | Completed |
| 4.3.2 | Repeat quantitative measures as above. |  |  | June 2008 | Requesting original data sets |
| 4.3.3 | Triangulation of quantitative data from qualitative field work. |  |  | October 2008 | Not commenced |

| 4.4a TRAINING OUR STAFF NB: there are only some agencies for whom it is relevant to complete a training project plan. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | ACC |  |
| Contributors |  |  |  | All agencies |  |
| Project Manager |  |  |  |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: - Assess available training options - Develop training that meets organisational needs - Plan and implement |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| To ensure frontline ACC staff are equipped with the skills and tools to respond to victims, spectators or perpetrators of Family Violence whether they be staff, clients of ACC or members of the communities in which ACC staff belong. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 4.4.1 | Frontline staff skills developed |  | 31/03/2008 |  | Work underway to scope requirements, attended MSD training |
| 4.4.2 | Establishment of specialist family Violence support people |  | 31/03/2008 |  | Scoping of ACC requirements. Initial training provider assesses did not meet requirements. |
| 4.4.3 | Training plan developed for all staff |  | 31/03/2008 |  | Modular based training identified as best solution – planned for May roll out. |

| 4.4b TRAINING OUR STAFF |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | All agencies |  |
| Contributors |  |  |  | CYF |  |
| Project Manager |  |  |  | MSD contact – Sarah James/Gerard Boomfield |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) |  |  |  |  |  |
| Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: - Assess available training options - Develop training that meets organisational needs - Plan and implement |  |  |  |  |  |
| Deadline |  |  |  |  |  |
| Purpose |  |  |  |  |  |
| So that frontline social work staff are able to recognise and respond to the dynamics present in situations of family violence. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 4.4.1 | Where identified as part of their professional development plan, frontline social work staff attend a Family Violence workshop |  | As scheduled in training calendar |  | A workshop has been available for some time, this is being reviewed as part of an ongoing quality assurance process and will now be available as part of the specialists stream within the new Practice Induction programme |
| 4.4.2 | Family Violence is discussed in numerous other parts of the new Practice Induction in the workplace learning modules, the classroom based two week Practice Foundation and various learning forums that are part of the new Practice Induction programme |  | As scheduled in training calendar |  | Ongoing |

# How this report works

The Ongoing Programme of Action Monitoring Report is organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure objectives remain on track.

- A monitoring report section – which includes two key parts:

  - A summary of the progress of each objective over the last three months and an overview of the work that is expected to occur over the next three months.

  - Summary information from the project plans for each objective.

The report format is new and still evolving. There are some objectives that require more information. The Secretariat will work to complete this information with the agencies responsible for these objectives over the coming weeks.

We have tried to layer the information provided in the report so that Taskforce members can get a snapshot of where things are at and refer to the Monitoring Report section for more detail on each objective, its milestones, and the responsible project managers within each agency if they wish to follow work up or find out more information.

The Taskforce’s planning and reporting hierarchy consists of the following:

- objectives – specific work that has been signalled in the programme of action

- actions –  specific work signalled in the programme of action, as part of an objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- key milestones – taken from individual agency project plans.

- We have also introduced a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to objectives and/or actions

- ensure the objective and actions remain relevant to the Taskforce and its priorities.

The variation process involves:

- completing the attached variation template

- consulting with appropriate Taskforce agencies over the changes to gain agreement and buy-in (this will be left to the responsible Taskforce agency seeking a variation to determine)

- sending a draft of the variation to the Secretariat to review before it is finalised, the Secretariat will then provide feedback and the variation can be finalised

- getting the responsible Taskforce member to sign the variation (thereby finalising the variation)

- sending the finalised variation to the Secretariat

- the Secretariat will brief the Taskforce Chair and seek his sign-off

- the Secretariat advise the agency seeking a variation of the outcome

- the outcome is noted in the Taskforce monitoring report.

A formal variation is required when a Taskforce agency wants to change an objective, action or both.  Formal variations are not required to change milestones, however, any milestone changes need to be provided to the Secretariat so that a log can be kept and changes can be tracked over time. Formal variations are not required for milestones because milestone changes should not compromise an objective and its associated actions.

A formal variation needs to be completed if the deadline for completion of an objective and associated actions changes. This is because the overall objective and actions are compromised.

The variation template is attached to this report, an electronic copy of which can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

- The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

- To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | Peter Hughes | Date |  |
| --- | --- | --- | --- |
| From |  |  |  |
| Security Level | In Confidence |  |  |
| request to amend Work Programme Objective or Action |  |  |  |
| Action | For your approval |  |  |

I am seeking your approval to change an objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted with the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| Xxxxx (Taskforce representative) |  |  |
| --- | --- | --- |
| XXXXX (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved  Not Approved  |  |  |