Ongoing Programme of Action

Monitoring Report

September 2008

Prepared by the Secretariat for the Taskforce for Action on Violence within Families

# Contents

Contents	3

Summary	5

Highlights	5

Hotspots	9

Variations	9

Alerts	9

Upcoming Objective Deadlines	10

Changes to Monitoring Process	11

Monitoring Report	13

Three Month Summaries and Milestone Updates	15

Leadership	15

1.1  Facilitation of the Ongoing Programme of Action (OPOA)	15

1.1a  Mapping of the Ongoing Programme of Action (OPOA)	16

1.2  Maori Programme of Action	16

1.3  Pacific Programme of Action	17

1.4  Child Maltreatment	18

1.5a  Family Violence Free Workplaces (MSD)	20

1.5b  Family Violence Free Workplaces (ACC)	23

1.5c  Family Violence Free Workplaces (NZ Police)	24

1.6  Iwi-Led Crime Prevention	25

1.7  Family Violence Clearinghouse	27

1.8  Case Studies Characterising Good Practice	27

1.9  Maori Research Agenda	28

1.10  Pacific Research Agenda	29

1.11  New Migrant and Refugee Research Agenda	30

1.12  Elder Abuse	31

1.13  Data on NGO Service Delivery	32

Changing Attitudes And Behaviour	36

2.1  Kia Puawai	36

2.2  Improving Attachment	36

2.3  Conduct Disorder / Severe Anti-Social Behaviour	38

2.4  Curriculum Development	39

2.5  Violence in the Media	42

2.6  Campaign for Action on Family Violence	43

2.7  Family Violence Death Review Project	45

Ensuring Safety And Accountability	48

3.1  Family Violence Courts	48

3.2  Protocols for Family Violence Courts	49

3.3  Social Services Supporting Courts	50

Effective Support Services	54

4.1  Maori Service Workforce Development	54

4.2  Pacific Service Workforce Development	54

4.3  Service Demand Data	55

4.4a  Training Our Staff	56

4.4b  Training Our Staff	57

First Programme of Action update	60

How this report works	66

# Summary

- The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions, which were later consolidated to 53 actions. A progress summary on these actions is provided towards the end of this report.

- The Taskforce’s Ongoing Programme of Action (OPOA) consists of 31 objectives which form the Taskforce’s work programme. To meet each objective, actions and milestones have been identified. This report provides a progress report against the objectives, actions and milestones.

- Any variation to objectives or actions requires a formal variation.  A variation template must be completed and signed by the appropriate Taskforce member, and then forwarded to the Secretariat for processing to final sign-out by the Taskforce. We are reviewing the sign-out process for variations. Changes have not yet been confirmed, all agencies will be contacted once further work has been done on this.

- For more information on this report, how it is organised and the current formal variation process, please refer to the “how this report works” section at the end of the document.

Objective status

| On track | 22 |
| --- | --- |
| Complete or ‘Business as Usual’ | 3 |
| Alerts | 2 |
| Variations | 4 pending |
| Total number of objectives | 31 |

There are six objectives for which the first phase has been completed.

## Highlights

This section provides an overview of key Taskforce initiatives for the reporting period of beginning of June 2008 to end of August 2008.

### Leadership

### Maori Programme of Action

- Iwi Leaders and Maori family violence practitioners have committed to the Maori Reference Group’s (MRG) Programme of Action (POA).  The Taskforce for Action on Violence within Families has signed-off MRG’s POA that involves Maori, the Family Violence sector and Government working together in addressing the issues, and developing effective actions, that will achieve zero tolerance of whanau violence.

### Pacific Programme of Action

- The Pacific Programme of Action was agreed to by the Taskforce at the 6 August 2008 meeting.  The next step will be to further develop the action areas in consultation with lead agencies.

### Domestic Violence Act 1995 Review

Cabinet approved amendments to the Domestic Violence Act 1995 and related legislation in May this year.   The Domestic Violence Reform Bill is currently being drafted by the Parliamentary Counsel Office.  It may be introduced shortly, subject to Parliament’s timetable.

### Child Maltreatment Prevention

At the 6 August meeting, the Taskforce agreed to make child maltreatment prevention a strategic priority for 2008 – 2011, and agreed the scope (child abuse and neglect), the focus (prevention) and the priorities for its actions.  Work is now focussed on getting projects up and running.

### Changing Attitudes and Behaviour

### Campaign for Action on Family Violence

There were 35 successful applicants in the third round of the Community Action Fund. The fourth round will open for applications in February 2009.

A third survey into the reach and retention of the TV advertisements is being conducted (September 2008). The last survey showed 89% of those surveyed remembered the adverts with one in five people of those who remembered the adverts taking some action. Preliminary results of a nationwide face-to-face survey that will specifically explore attitudes about violence towards women, inter-partner violence, and child abuse will be available in October 2008. A community study is underway that will provide an in-depth analysis of the impact of the campaign.

### Family Violence Death Reviews

The Family Violence Death Review Committee has been established and appointed. The inaugural members were appointed by the Associate Minister of Health, for the Minister of Health on 6 August 2008.  The members are as follows:

- Wendy Davis (Chairperson)

- Ngaroma Grant

- Brenda Hynes

- Dr Patrick Kelly

- George Ririnui

- Dr Alison Towns

- Rob Veale

- Vaoga Mary Watts

The FVDRC’s induction day will be on 1 October and the Committee will hold its first meeting on 2 October 2008.

### Ensuring Safety and Accountability

### Family Violence Courts

The Chief District Court Judge has confirmed Palmerston North and Whangarei as the locations for the new Family Violence Courts.  The Palmerston North Family Violence Court will be operational from 12 September 2008.  The Whangarei Family Violence Court is likely to be operational in April 2009.

- Family Violence Court training

- Staff/stakeholder training and consultation has been completed for the two new Family Violence Courts.

- National Operating Guidelines

Consultation on the National Operating Guidelines for Family Violence Courts is complete.  The Guidelines have been endorsed by the Chief District Court Judge and approved by the Ministry of Justice. The Guidelines were issued to staff on 8 September 2008.  Taskforce members were also sent a copy of the guidelines.

### Social Services Supporting Family Violence Courts

The Project Plan and Terms of Reference for this objective have been finalised and agreed. The Ministry of Justice has begun work on developing the role of an independent victim advocate / support person to provide support and assistance to victims of domestic violence in the Family Violence Courts in conjunction with MSD.  The Ministry of Justice has begun consulting internally and with Police. A workshop was held in early August with NGOs and external government agencies.  From this consultation a draft role description has been developed and the Judiciary is currently being consulted on this draft.  Consultation with NGOs and external government agencies on the draft role description will begin in early September.

In February 2008, the Government announced increased funding for non-mandated stopping violence programme providers for offenders. From 1 July 2008, processes have been put in place at each Family Violence Court to manage funding of non-mandated programmes.

### Effective Support Services

### Pathway to Partnership

The Pathway to Partnership working group are well through the process of working with social service family violence service providers to establish and confirm their final 2008/09 funding increases.  It is expected that this process will be complete by the end of September.

From here, planning on how communities, government and the sector work together to deliver high-quality, effective services to families, children and young people will progress.

As the next phase of Pathway to Partnership progresses, there will be a focus on how agencies work together to achieve the results we want to see in our communities. While additional funding is a key component, Pathway to Partnership is, just as importantly, about changing the way agencies work together and work with families.

## Hotspots

This section highlights objectives that are subject to variation or have been identified as areas of risk. All objectives not mentioned in this section are on track to be completed as planned.

### Variations

Variations are formal requests for changes to objectives and/or actions in the Taskforce’s Ongoing Programme of Action. This table includes all approved Variations of objectives from the Ongoing Programme of Action.

| Approved variations |  |  |  |
| --- | --- | --- | --- |
| Objective | Title | Variation summary | Status |
| 3.3 | Social Service Supporting Courts | The objective remains the same, changes to the actions required. The variation was requested due to the need to align with the direction the Chief District Court Judge has set for the Family Violence Courts, and to ensure consistency with a 2008 Budget bid. | Approved 4 April 2008. |
| 2.4 | Curriculum Development | The objective remains the same, changes to the actions required. “Whole school strength-based approaches” could not be extended due to an increase in costs for delivery of student wellbeing contracts. The use of this approach is being strengthened by incorporating successful professional learning approaches for student wellbeing in the design and delivery of ongoing professional development contracts. | Approved 28 March 2008. |

### Alerts

This table highlights areas that have been identified as at risk of not being delivered.

| Objective | Title | Issue | Mitigation |
| --- | --- | --- | --- |
| 1.1a | Mapping of the Ongoing Programme of Action | The objective and actions for this work need to be clarified. | The Secretariat will follow up with NGO Taskforce members. |
| 1.11 | New migrant and refugee research agenda | Development of scoping paper delayed. Final deadline will be determined from scoping. Key milestone date moved from June to December 2008. | Work has begun on developing a scoping paper setting out options for possible research projects and recommendations for next steps for the Taskforce meeting in December. |

### Upcoming Objective Deadlines (next two months)

This table highlights Objective deadlines that are due over the next two months, or that have been completed and further deadlines need to be defined. If deadlines are not likely to be met, agencies should contact the Secretariat to discuss a possible variation.

| Objective | Title | Agency | Objective Deadline |
| --- | --- | --- | --- |
| 1.2 | Maori Programme of Action | Maori Reference Group / Ministry of Social Development | September 2008 |
| 1.3 | Pacific Programme of Action | Pacific Advisory Group / Ministry of Social Development | November 2008 |
| 1.8 | Case Studies Characterising Good Practice | Ministry of Social Development | October 2008 |
| 1.9 | Maori Research Agenda | Te Puni Kokiri | 5 September 2008 |
| 1.12 | Elder Abuse | Ministry of Social Development | October 2008 |
| 4.2 | Pacific Service Workforce Development | Ministry of Social Development | July 2008 |
| 4.3 | Service demand data | Ministry of Social Development | October 2008 |

## Changes to Monitoring Process

The Secretariat is currently in the process of reviewing objectives, actions and purpose statements, and appropriateness and focus of the project plan tables for each objective. As part of this review it has been noted that some project plans don’t have a purpose statement. The Secretariat is looking to get these clearly defined. The Secretariat will also be looking to ensure that work outlined in key milestones relates to objectives and purpose statements. The Secretariat will also be making sure that objectives and actions are outcome focussed, rather than process focussed, with the understanding that process milestones are important in tracking work towards outcomes.

Changes to the Variation Request Process

It is very important to have a robust and transparent process for varying objectives, actions and key milestones. A transparent variation process was implemented when monitoring of the Ongoing Programme of Action began at the beginning of 2008.  The Secretariat is now considering how to build on and strengthen this process further. A variation process that involves the Taskforce approving major changes is likely to be developed.

The variations below have not yet been approved, and will be progressed once the variation process is finalised.

| Objective | Title | Variation summary | Status |
| --- | --- | --- | --- |
| 1.9 | Maori Research Agenda | There has been some delay to this project due to availability of specialist Maori contractors, case study organisations and the expert steering group. A revised deadline of 5 September 2008 has been requested. | Submitted 18 July. |
| 1.10 | Pacific Research Agenda | Changes to actions have been requested, although the objective will remain the same. Further development of the project plan has clarified actions required to achieve Taskforce objectives. | Submitted 23 June. |
| 3.1 | Family Violence Courts | The objective remains the same. The objective deadline has been missed; the deadline for final establishment of the two Family Violence Courts has been requested to be revised to early 2009. | Submitted 31 July by the Judiciary (through MoJ). |
| 4.2 | Pacific Service Workforce Development | This project plan is now part of the Pathway to Partnership work on workforce provider capacity and capability. Although a project plan was completed within the deadline, the Steering Group has decided that other areas are of first priority. | Submitted 22 July. |
| Action 66 (first programme of action) | Determine level of attendance and performance of perpetrators at programmes | The Ministry of Justice is currently collating and analysing data. A final report will be completed by 30 September 08. The results from this will be used to inform Action 67. | Submitted 31 July. |

# Monitoring Report

The Detailed Milestone Updates and Three Month Summaries section. This section outlines progress on each milestone and provides an update on work undertaken in the previous three months (June to August) and work which is upcoming in the next three months (September to November).

## Three month summaries and milestone updates

This section provides updates on each milestone, and updates on both work undertaken in the previous three months and work planned for the upcoming three months.

### Leadership

| ### 1.1 FACILITATION OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Taskforce Secretariat / All Taskforce agencies |  |
| Project Manager |  |  |  | Carra Hamon |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) Facilitation, implementation and strategic engagement of the Ongoing Programme of Action for specific groups and across all sectors in New Zealand. Actions include: - stewardship of the Ongoing Programme of Action work programme - stewardship of children specific work programme - stewardship of all other work programmes. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose To successfully monitor and ensure implementation of the Ongoing Programme of Action. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.1.7 | Protection Orders update to be sent to Minister. |  | April 2009 |  | Delayed until March/April 2009. Delay will enable a full one-year progress report to be developed. |
| 1.1.9 | Review of all objectives, actions and milestones in the Monitoring Report. |  | Complete by end 2008 |  | As directed by the Chair of the Taskforce. This will include a review of the variation process. |
| 1.1.10 | Monitoring Report for September prepared and sent with 1 October meeting papers. |  | 18 Sept |  | On track. |
| Progress to date (previous 3 months work) - There has been some feedback on the Monitoring Report format and variation process. Further feedback is encouraged. - A first draft of the six-month report on the Waikato University research on Protection Orders was prepared. - The Taskforce has accepted recommendations on ‘Additional Taskforce meetings’ and ‘Taskforce protocol for sharing information’, as distributed at the August meeting. Current ongoing work (next 3 months) - Preparing the Monitoring Report for the 1 October 2008 Taskforce meeting. - Organising the agenda and the papers for the next Taskforce meeting and assisting in the organisation of the Multi-Party Group. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.1a MAPPING OF THE ONGOING PROGRAMME OF ACTION (OPOA) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | NGOs |  |
| Contributors |  |  |  |  |  |
| Project Manager |  |  |  |  |  |
| Objective and actions (as per Work Programme) Actions include: - Ongoing Programme of Action mapped to its outcome. |  |  |  |  |  |
| Objective deadline |  | TBC |  |  |  |
| Purpose TBC |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.1a.1 | Definition of this objective |  | 1 July 2008 |  | NGO Taskforce members approached to discuss this objective. |
| Alert: Next steps to be confirmed. |  |  |  |  |  |

| ### 1.2 MAORI PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agencies |  |  | Maori Reference Group (MRG) Ministry of Social Development |  |  |
| Contributors |  |  | Te Puni Kokiri, NGOs |  |  |
| Project Manager |  |  | Ann Dysart (MSD) |  |  |
| First Programme of Action reference |  |  | Action 7 |  |  |
| Objective and actions (as per Work Programme) A Programme of Action focused on eliminating violence in Maori whänau is developed. Actions include: - developing a Maori Programme of Action - ensuring the leadership and ownership of the actions at all levels of Te Ao Maori - ensuring all designated Actions are monitored and achieved. |  |  |  |  |  |
| Objective deadline |  | New deadline to be defined by September 2008 (see Key Milestone 1.2.5) |  |  |  |
| Purpose - To develop a process and plan that engages all areas of Te Ao Maori in owning and addressing the issues of Family Violence and Child Abuse - To progress implementation of MRG’s Action Plan in order to achieve zero tolerance of whanau violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 1.2.3 | Local regional hui with Maori family providers and practitioners. |  |  | April / May 08 | Regional Hui have been completed. Analysis of the discussions is due to be completed by mid September, when findings will be disseminated to MRG and attendees of the hui. |
| 1.2.4 | Launch Maori Programme of Action (MPOA). |  |  | June 08 | The draft MPOA was signed-off by the Taskforce at their meeting on 6 August. |
| 1.2.5 | Work towards establishing an action plan for 2008 - 2009 and priorities for next five years |  |  | August 08 | Action Plan for 2009 – 2013 has been developed and will be presented to MRG at the meeting set for 24 September. |
| Background The Taskforce’s MRG has developed a Maori Programme of Action (MPOA). Progress to date (previous 3 months work) - Regional Hui have been completed. - MRG’s Draft Programme of Action was presented to the Taskforce who signed it off at the same meeting on 6 August. Current ongoing work (next 3 months) - Collation of Regional hui notes for analysis and dissemination to MRG - Present to MRG the Action Plan for 2009 – 2013 - Work with agencies to ensure input into all key policy work. Timing / Ongoing / Recommendations / Conclusions Status = On track. The next deadlines will be defined from the MPOA once priorities have been finalised in September 2008. |  |  |  |  |  |

| ### 1.3 PACIFIC PROGRAMME OF ACTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Pacific Advisory Group (PAG) Ministry of Social Development |  |
| Contributors |  |  |  | Ministry of Pacific Island Affairs, NGOs |  |
| Project Manager |  |  |  | Liz Tanielu (MSD) |  |
| First Programme of Action reference |  |  |  | Action 7 |  |
| Objective and actions (as per Work Programme) Programme of Action focused on eliminating violence in Pacific families is developed. Actions include: - Develop a Pacific Programme of Action. - Hold discussions with agencies to confirm action areas of responsibility and process for implementation. - Develop the leadership action area to be coordinated by MSD with PAG. |  |  |  |  |  |
| Objective deadline |  | New deadline to be defined by November 2008 (see Key Milestone 1.3.6) |  |  |  |
| Purpose To articulate the status of Family Violence as it impacts on Pacific People and outline specific actions to address it. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.3.2 | Stakeholder Meetings for input into POA |  | March 08 |  | Complete. |
| 1.3.3 | Final POA |  | June 08 |  | Complete. The Pacific POA was completed and agreed at the 6 August Taskforce meeting. |
| 1.3.4 | Release of Pacific POA |  | Sept 08 |  | On track. |
| 1.3.5 | Hold discussions with agencies on the action areas and implementation process. |  | Oct 08 |  | On track. |
| 1.3.6 | Finalise implementation timeline and actions areas. |  | Nov 08 |  | On track. |
| Progress to date (previous 3 months work) - The draft Pacific POA was tabled at the Taskforce meeting on August 6. The Taskforce agreed to the Pacific POA and for government Taskforce members to nominate senior officials from their agencies to discuss the action areas and implementation process with the Project Manager. Current ongoing work (next 3 months) - To commence discussions with government agencies on the implementation phase of the POA. - PAG to outline the implementation process for the Leadership action area. - PAG to provide advice on projects within the OPOA, including Pathways to Partnership, the Family Violence Campaign, the Pacific Research Agenda and Child Maltreatment Prevention. Timing / Ongoing / Recommendations / Conclusions Status = First phase completed to mid 2008. The next deadlines will be defined by November 2008, as per Key Milestone 1.3.6. |  |  |  |  |  |

| ### 1.4 CHILD MALTREATMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Office of the Children’s Commissioner |  |
| Contributors |  |  |  | MSD, NGOs, Justice, Health, Education, Police |  |
| Project Sponsor |  |  |  | Dr Cindy Kiro |  |
| Project Manager |  |  |  | John Angus / Ruth Palmer (MSD) |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) The objective of the first phase was to develop a work programme on preventing child maltreatment by 30 June 2008. This was completed (reported in the July Monitoring report). The objectives of the second phase are to agree and then carry out the work programme. The work programme comprises an integrated, cross sector approach to preventing child maltreatment. It draws on a growing evidence and knowledge base about the impacts of maltreatment. |  |  |  |  |  |
| Objective deadline |  | 30 June 2009 (second phase) |  |  |  |
| Purpose The Taskforce has agreed to give priority to the prevention of child maltreatment over the next three years, and has agreed the scope, focus and priorities of the proposed work programme. The purpose of the work for 2008 – 2009 is to: - Enhance the contribution of the health, education and social services sectors to prevention of child maltreatment. - Understand better and take actions to reduce the incidence and prevalence of neglect, in particular of 0 – 5 year olds. - Strengthen effective community responses. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.4.5 | Work programme agreed |  | August 2008 |  | Completed. Presented at August meeting and generally agreed, with some further refinement of project deliverables. |
| 1.4.6 | The nine background work programme scoping papers are finalised |  | August 2008 |  | Completed. |
| 1.4.7 | Project plans for the nine projects are completed |  | September 2008 |  | On track. Draft versions underway and due to be completed by 30 September. |
| 1.4.8 | Complete the review of the Health, Education and Social Service Sector Contributions to child maltreatment (3 of the 9 projects) |  | 31 March 2009 |  | To be commenced 1 October 2008. |
| 1.4.9 | Undertake research into neglect |  | 30 June 2009 |  | To be commenced 1 October 2008. |
| 1.4.10 | Prepare advice on a child maltreatment prevention phase of the Campaign |  | 31 August 2008 |  | Will be reported at 1 November meeting. |
| 1.4.11 | Commence a child maltreatment phase of the Campaign |  | 30 June 2009 |  | On track. |
| 1.4.12 | Take actions to work with communities to strengthen their preventive responses to child maltreatment including: - gathering evidence for what works by 31 December 2008 - providing greater support for successful community approaches by 31 March 2009 - supporting philanthropic sector plans for a trial of new approaches and commencing an evaluation of any trial by 30 June 2009. |  | 30 June 2009 |  | On Track. |
| Background The Ongoing Programme of Action, includes developing a work programme on child maltreatment (including child sexual abuse) that: - focuses on improving outcomes for children - takes account of the different types of child maltreatment - identifies priority areas where the Taskforce can make a difference. Progress to date (previous 3 months work) - The Working Group meets fortnightly, and since developing the work programme has taken on a governance role over the development of the projects. - The External Advisory Group (EAG) met on 22 July and is scheduled to meet on 4 November with Taskforce members. The EAG will continue to be available for expert advice throughout 2008 – 2009. - The Taskforce approved the scope, focus and priorities of the draft work programme at the August meeting. Work has commenced on project plans for all nine projects. The work programme consists of nine specific areas of work across the four fronts of the Taskforce programme. It has three priority areas of action: neglect; reviews of the education, health and social services sector contributions; and working with communities to keep children safe and secure. - The scoping papers that support the work programme have been developed. Current ongoing work (next 3 months) - Develop and complete the project plans for the nine projects. - Commencing work on the agreed 2008 – 2009 outputs. Timing / Ongoing / Recommendations / Conclusions Status = on track |  |  |  |  |  |

| ### 1.5a FAMILY VIOLENCE FREE WORKPLACES (MSD) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | MSD |  |
| Contributors |  |  |  | ACC, Police, NGOs |  |
| Project Manager |  |  |  | David Dick |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) Family Violence-Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector |  |  |  |  |  |
| Objective deadline |  | May 2012 |  |  |  |
| Purpose Family Violence Free Workplaces means staff in those workplaces are aware and supported around issues to do with family violence. These workplaces are expected to provide low cost, high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Free Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.5a.2 | Policy development |  | Dec 2008 |  | Draft completed. PSA consulted. Further business group and service line consultation is progressing prior to taking policy to MSD Leadership Team for consideration. |
| 1.5a.4 | Manager guidelines developed to support policy. Published on MSD intranet site |  | See 1.5a.2 |  | Draft guidelines are completed and subject to Policy being approved. – see 1.5a.2 for revised date. |
| 1.5a.5 | Raising Awareness of Family Violence - Regional info sessions |  | Dec 2008 |  | A needs assessment for delivering regional information systems has been completed. It is considered that due to service line specific training that already supports family violence awareness, specific regional information sessions are not required. Further awareness raising will be addressed through ongoing Ministry promotional material and resources (such as 1.5a.6) |
| 1.5a.6 | Providing accessible information and resources - Provide informational resources for workplaces – such as posters, booklets, toolkits |  | Dec 2007 |  | Complete. Resources from the Family Violence (FV) Campaign distributed to business units. |
| 1.5a.7 | Tools and resources - address concerns about Family Violence counselling services available through current EAP provider - Explore the development of web-based family violence resources for the workplace |  | Oct 2007 2009 |  | Completed. Will monitor to identify if issues regarding availability of family violence counselling services have been resolved (still too early to comment on this). This activity is completed for MSD HR. MSD HR have suggested that Preventing Violence in the Home (PVH) and MSD Family and Community Services explore this further subject to their mutual interest in web-based training tools. Still in earlier exploration stages. |
| 1.5a.8 | Training - Deliver additional training programmes for key support people and all staff as required |  | As required |  | Business as usual, so no further updates. |
| 1.5a.9 | Peer support framework developed - approval - developed - pilot - track and assess roll-out to other areas. |  | Dec 2008 |  | Complete. Next review meeting scheduled for Nov 2008. |
| Overall Context The current HR plan to support the goal of becoming a family violence free workplace involves a longitudinal approach founded on raising and maintaining staff awareness of family violence - the workplace impacts and supports. Information sharing across other Taskforce contributors (ACC and NZ Police) will continue. 1.5a.2 Policy development Background The purpose of the family violence policy is to raise awareness of the impact of family violence in the workplace and to provide and raise awareness of the support mechanisms for employees who are experiencing family violence, want assistance to help others, or want assistance to stop their violence. Progress to date (previous 3 months work) - PSA have been consulted and provided support to the draft policy. The draft Policy is currently with the Child, Youth and Family service line for consideration by their Executive Management team. Current ongoing work (next 3 months) - Progress the draft policy through the approval process and plan for its implementation. Subject to endorsement by the Child, Youth and Family service line we propose to take the draft policy to the MSD Leadership team for consideration. Timing / Ongoing / Recommendations / Conclusions Status = On track. 1.5a.4 Manager guidelines developed to support policy Current ongoing work (next 3 months) - No further developments this quarter. Will be progressed in conjunction with 1.5a.2. The Manager Guidelines have been developed as a companion resource to the family violence policy and will be implemented once the family violence policy has been approved. Timing / Ongoing / Recommendations / Conclusions Status = Ongoing. Subject to 1.5a.2. 1.5a.5 Regional information sessions Background The information sessions are part of the broader “family violence awareness raising” activities. Current ongoing work (next 3 months) - A needs assessment for delivering regional information systems has been completed. It is considered that due to service line specific training that already supports family violence awareness, specific regional information sessions are not required. Further awareness raising will be addressed through ongoing Ministry promotional material and resources. Timing / Ongoing / Recommendations / Conclusions Status = Ongoing. Milestone completed but planned activity not required following results of needs assessment. 1.5a.7 Tools and resources Ongoing (long term) - Exploring options for the development of web-based family violence resources for the workplace, with implementation in 2009. Development of tools was subject to mutual interest between other agencies. HR has facilitated initial connections but is in no position to further progress this initiative. Timing / Ongoing / Recommendations / Conclusions Status = Complete 1.5a.8 Training Training will be planned and delivered subject to demand. This is now business as usual –training within specific business areas is already built into training curriculum (eg Work and Income) Timing / Ongoing / Recommendations / Conclusions Status = Business as usual. |  |  |  |  |  |

| ### 1.5b FAMILY VIOLENCE FREE WORKPLACES (ACC) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  |  | Accident Compensation Corporation |  |
| Contributors |  |  |  |  | MSD, Police, NGOs |  |
| Project Manager |  |  |  |  | Danielle George |  |
| First Programme of Action reference |  |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Family Violence Free Workplaces are developed and implemented through HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector. |  |  |  |  |  |  |
| Objective deadline |  |  | December 2008 |  |  |  |
| Purpose Family Violence Free Workplaces means staff in those workplaces are aware and supported around issues to do with family violence. These workplaces are expected to provide low cost high impact prevention and recovery opportunities for members of the workplace who are affected by family violence. They may be victims, observers or perpetrators. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |  |  |
| Key Milestones |  |  |  | Date |  | Description of Progress |
| 1.5b.3 |  | HR Co-ordinator skills development |  | Sept 2008 |  | Complete. A partnership approach with Stratos has been developed and launched to ACC staff as part of Safety NZ Week – Safety in the Home. The support package allows for individual support for staff, managers and HR people for people impacted by family violence. This initiative replaces the original plan to train HR and contact people across the organisation. Staff and HR feedback was very poor following the initial training package. As a result the alternative partnership approach with Stratos was designed, developed and implemented. |
| 1.5b.4 |  | Training programmes and managers’ guides |  | 31 Oct 2008 |  | Completed and in place – published to staff and managers via staff Intranet. Additional promotion planned as part of White Ribbon Day (25 Nov 2008). |
| 1.5b.5 |  | Policy and guideline refresh |  | 31 Oct 2008 |  | Complete. Launched as part of ACC’s Staff Wellbeing programme in February 2008. A launch of the phase two refresh is also planned for White Ribbon Day (25 Nov 2008). |
| 1.5b.7 |  | FV and FW Support programme |  | 31 July 2008 |  | External support programme developed to provide 1:1 support for staff, HR team and managers. Website and service launches 31 July 2008, including access via text service. |
| 1.5b.6 | Family Violence Free Workplaces (FVFW) established across ACC |  |  | 31 Dec 2008 |  | On track to be fully embedded across ACC by end of 2008. |
| Progress to date (previous 3 months work) - Staff and HR feedback was very poor following the initial training package in early 2008. As a result the alternative partnership approach with Stratos was designed, developed and implemented. - Training programmes and managers’ guides in place - published to staff and managers via staff Intranet. - All programmes are now on track and in place. The next phase will be to review the effectiveness of the support packages at the 6 month mark on 31 December 2008. - Next steps for the development of workplace policy that extends outside the workplace will need to be researched over the next period Current ongoing work (next 3 months) - Relaunching support package and policy to complement White Ribbon Day (25 Nov 2008). - Develop ongoing communications plan to ensure staff awareness and track progress of programme. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |  |

| ### 1.5c FAMILY VIOLENCE FREE WORKPLACES (NZ Police) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | New Zealand Police |  |
| Contributors |  |  | MSD, ACC, NGOs |  |
| Project Manager |  |  | Carol Train |  |
| First Programme of Action reference |  |  |  |  |
| Objective and actions (as per Work Programme) Family Violence -Free Workplaces are developed and implemented through Police HR policy – link to Campaign, model for other agencies, role model for public and other workplaces. Actions include: - develop policy - put in place tools and resources - training of contact people/family violence co-ordinators - implementation - develop a model for replication in the public sector and private sector. |  |  |  |  |
| Objective deadline |  | May 2012 |  |  |
| Purpose Family Violence Free Workplaces will raise the awareness of staff in the Police about family violence and provide support where appropriate. Police staff may be victims, observers or perpetrators of family violence. Implementing Family Violence Workplaces is expected to decrease workplace stress, and increase workplace productivity by empowering and supporting victims and observers of family violence and channelling perpetrators through appropriate channels to help them change their behaviour. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 1.5c.1 | Policy developed and agreed |  | Dec 2008 | On track, policy is on second draft. Have met with MSD to update on progress. |
| 1.5c.2 | Training and resource developed |  | Dec 2009 | On track. |
| 1.5c.3 | Communications package completed |  | Jan 2010 | On track. |
| 1.5c.4 | Training Delivered in all Districts |  | Dec 2010 | On track. |
| 1.5c.5 | Family Violence Free Workplaces established in Police |  | TBC | On track. |
| 1.5c.6 | Evaluation of Police model |  | Dec 2011 | On track. |
| 1.5c.7 | Finalise Blueprint for implementing Family Violence Free Workplaces in public, private and non-government sectors |  | May 2012 | On track. This Blueprint will be a collaborative work between Police, MSD and ACC. |
| Progress to date (previous 3 months work) - The second version of the draft policy has been completed. - The internal working group (consisting of representation from HR, Policy, Operations and District) has met for the second time to develop the policy and will give feedback on version two. Current ongoing work (next 3 months) - The formal consultation phase will take place and the completed policy will be signed off by PEM by the 31 December 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |

| ### 1.6 IWI-LED CRIME PREVENTION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | New Zealand Police |  |
| Contributors |  |  |  | Iwi, NGOs, Te Puni Kokiri |  |
| Project Manager |  |  |  | Wally Haumaha |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) Iwi-led crime prevention plans which have a focus on the prevention of family violence Actions include: - provide support to iwi to develop plans - Iwi-led crime prevention strategies developed in accordance with each iwi identified needs, values and timeframes. |  |  |  |  |  |
| Objective deadline |  | The NZ Police state that this is an iterative and evolving process that is being driven by iwi. Precise deadlines are neither available, nor appropriate at this stage. |  |  |  |
| Purpose In absolute numbers, a high number of Maori churn through the criminal justice system every year. A new framework for action is being developed by Maori with assistance from officials. That new framework is Iwi-led Crime Prevention Plans (ICPPs). ICPPs take a long-term, incremental approach to improving Maori criminal justice outcomes. They are led by iwi, with assistance from officials. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.6.1 | Iwi to populate their crime prevention plan templates |  | No deadline |  | On track |
| 1.6.2 | Officials to condense those templates into A3 summaries |  | No deadline |  | Pending |
| 1.6.3 | Summaries to be presented back to iwi for confirmation |  | No deadline |  | Pending |
| 1.6.4 | Ministerial briefing paper to Ministers of Justice, Police and Maori Affairs |  | March 2008 |  | Complete |
| Background recent work (2007/2008) Police and Te Puni Kökiri have been supporting iwi with the necessary tools to develop and design their own Plans. The type of support provided includes: - providing Police intelligence to iwi groups that enable iwi to understand the crime problems and profiles of Mäori (offenders and victims) within their geographical areas. - providing specialised trained staff who are able to take iwi through a formal problem solving approach to crime prevention crime prevention methodology training in SARA and POP models - providing draft Iwi Crime Prevention Plan templates and Guidance Notes for preparation of the Iwi Plans - funding writers nominated by iwi to begin drafting iwi-specific crime prevention plans. Progress to date (previous 3 months work) - Amendments have been made to Te Arawa plan, following public submissions and substantive approval from iwi. - Ngati Whatua and Tainui ki te tonga have developed a governance structure and Charter to underpin a joint plan for Auckland-metro. A writer has been appointed, but awaits terms of reference. - Ngapuhi have appointed a writer who has already begun work on their plan. - A writer for Waikato has been appointed and will begin writing the plan soon. - Te Tau Ihu had already prepared a crime prevention plan prior to the commencement of the iwi-led crime prevention plan (ILCPP) process. Current ongoing work (next 3 months) - Police are continuing to work with iwi across all Police districts. - An initial engagement is being organised with Ngati Porou (Eastern District). - Further work is required among South Island iwi to confirm whether they will prepare separate/joint plans, who will fund writers, and how best to align the pre-existing Te Tau Ihu plan with other ILCPPs. - Finalised plans will be reviewed, summarised and consolidated by officials. - Inter-agency working group (NZP, TPK, MoJ) has met once and will re-convene soon, now that Police policy group have increased capacity to assist MPES in leading this work. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.7 FAMILY VIOLENCE CLEARINGHOUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | Families Commission, NGOs |  |
| Project Manager |  |  |  | Jeff Sheerin |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) The New Zealand Family Violence Clearinghouse (NZFVC) is enhanced to ensure its efficacy and to become the independent, sustainable, comprehensive one-stop shop for national and international information on family violence. Actions include: - develop a model and systems which optimise the operations of the NZFVC. |  |  |  |  |  |
| Objective deadline |  | June 2009 |  |  |  |
| Purpose To review NZ Family Violence Clearinghouse activities and services and develop a strategy for moving forward. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.7.1 | Negotiate contract with Canterbury University |  | 30 Jan 2008 |  | Complete. Negotiations concluded April 2008. The extended contract expired on 31 August 2008. |
| 1.7.2 | Scope redevelopment of NZFVC project, identify requirements and develop strategy |  | September 2008 |  | Now underway. A project manager for the NZFVC redevelopment has been appointed to lead this work. |
| 1.7.3 | Develop 2-5 year strategy |  | 30 June 2009 |  | This work is dependent on human resource availability. |
| 1.7.4 | Develop project plan and secure funding |  | September 2008 |  | Now underway on basis of planning for long term sustainable clearinghouse website from 1 March 2009. |
| 1.7.5 | Implement new clearinghouse website and service |  | 28 February 2009 |  | Planning now underway and initial work definitions document developed with MSD IT. February 2009 is revised milestone date. |
| Progress to date (previous 3 months work) 1.7.1 - The contract for the provision for a NZFVC for the 2007-2008 year was approved and signed by MSD and the University of Canterbury. The contract, providing for an additional two months of services for the Clearinghouse, expired on the 31 August 2008. Management and the NZFVC team have developed an interim service to maintain the Clearinghouse website while development of a new NZFVC takes place from 1 September 2008. 1.7.2 - Work has commenced on gathering requirements for a new NZFVC website on the basis of bringing the IT operations for the NZFVC in-house to MSD. Development work will also include developing user needs and ideas around the look and feel of a new NZFVC website. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.8 CASE STUDIES CHARACTERISING GOOD PRACTICE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs, Justice, Police |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Case studies characterising good practice in service aimed at eliminating family violence are developed and made publicly available. Actions include: - scope and identify existing good practice models - record the characteristics of their success - index and deposit in Family Violence Clearinghouse. |  |  |  |  |  |
| Objective deadline |  | October 2008 |  |  |  |
| Purpose To describe and generalise good practice principles as they apply to family violence prevention. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.8.2 | Draft case studies |  | Sept 2008 |  | Completed |
| 1.8.3 | Final case studies |  | Oct 2008 |  | On track |
| Background Current evaluative activities will be used to identify good practice models. The project will commence by drawing on one of the evaluative activities that support the Campaign for Action on Family Violence (the Campaign). The case studies will therefore focus on the practice of family violence prevention through social marketing. The aim of the evaluation project is to investigate and illustrate the impact of the Campaign on selected communities. It will focus on collecting information on observable and recorded changes relating to family violence over time in selected communities. As part of this evaluation two case studies will be produced that illustrate and explain “significant changes” arising from the Campaign. Progress to date (previous 3 months work) - Data collection is complete, and draft case studies have been compiled. Current ongoing work (next 3 months) - Case studies will be finalised, any additional data collection completed. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.9 MAORI RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Te Puni Kökiri |  |
| Contributors |  |  |  | MRG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | Te Atarangi Whiu |  |
| First Programme of Action reference |  |  |  | New initiative |  |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in whänau Mäori and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | 5 September 2008 [Variation request submitted] |  |  |  |
| Purpose To increase the evidence base by providing case studies of a minimum of three Maori designed, developed and delivered programmes. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.9.1 | Progress Report |  | 31 Jan 08 |  | Completed. Scope of project defined. Three key outputs. |
| 1.9.2 | Key findings presentation to Taskforce meeting |  | 6 Aug 08 |  | Complete. |
| 1.9.3 | Final Report |  | 5 Sep 08 |  | Strong progress made, previous delays due to provider availability and consultation. This report will be presented at the October Taskforce meeting. |
| Background Te Puni Kōkiri is working to identify current information regarding family violence for Maori, and looking at culturally distinct models of prevention and intervention for Maori. It is expected that an agenda for research will emerge from this work. Three key outputs for this work were identified: Output One: A literature review intended to identify current information on Maori family violence; information gaps; inconsistencies; and themes within the literature on family violence and Maori. Output Two: A case study analysis of existing Maori designed, developed and delivered initiatives that address family violence. Output Three: A summative report that analyses output one and two and identifies research priorities to form a Maori Research Agenda. Progress to date (previous 3 months work) - Key deliverables completed include draft framework of the Summative Report, three case studies and literature review. - The final summative report will be submitted on 5 September. The Summative Report will identify key research priorities for Maori and family violence through a comparative analysis between the literature review and case studies. Te Puni Kokiri has requested that the Maori Research Agenda be included at the October Taskforce meeting where key findings from this research will be presented. Current ongoing work (next 3 months) - Finalising the Summative Report with sector experts and preparing presentation of key findings for the October Taskforce meeting. Timing / Ongoing / Recommendations / Conclusions Status = Variation submitted for delayed timing. |  |  |  |  |  |

| ### 1.10 PACIFIC RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Pacific Island Affairs (MPIA) |  |
| Contributors |  |  |  | PAG, MSD, Families Commission, NGOs |  |
| Project Manager |  |  |  | David Schaaf |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) A Variation was submitted in July 2008, awaiting approval. |  |  |  |  |  |
| Improve our understanding of the nature of family violence in Pacific families and successful models of prevention and intervention. Actions include: - finalise project plan - consultation with Pacific Advisory Group (PAG) - consultation with other Pacific stakeholders - development of report including; - identification of Pacific Family Violence Research priorities - development of a research agenda linked to the Taskforce strategic research agenda - recommending further action. |  |  |  |  |  |
| Objective deadline |  | Final deadline to be confirmed. |  |  |  |
| Purpose To develop an understanding of Pacific family violence research priority topics and the issues which surround Pacific family violence research. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.10.1 | Finalise project plan |  | April 2008 |  | Complete. Project plan finalised, stakeholder discussions completed. |
| 1.10.2 | Consult with Pacific Advisory Group |  | June-July 2008 |  | Initial discussion has commenced. |
| 1.10.3 | Consult with other Pacific stakeholders |  | August 2008 |  | Not yet commenced. |
| 1.10.4 | Completion of report |  | September 2008 |  | Not yet commenced. |
| Background The Pacific Family Violence Research Agenda will sit within a Pacific Research Agenda. Progress to date (previous 3 months work) - The second meeting with PAG did not go ahead due to a postponed PAG meeting. This meeting will now take place on 15 October. Current ongoing work (next 3 months) - MPIA will be meeting with Elizabeth Powell, Director Pacific Development at Counties Manukau District Health Board, to discuss their work to develop a Pacific Research Agenda and gaps analysis. - In October, MPIA will consult with PAG again about what research on Pacific family violence is needed both now and in the future. MPIA will also go through a prioritisation exercise with PAG. A wider stakeholder group will later be brought together for consultation. A report will be developed which will outline the issues associated with Pacific family violence research and culminate in the development of Pacific family violence research priority topics. Timing / Ongoing / Recommendations / Conclusions Status = some delay. Awaiting approval of the variation submitted 23 June 2008. |  |  |  |  |  |

| ### 1.11 NEW MIGRANT AND REFUGEE RESEARCH AGENDA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Improve our understanding of the nature of family violence in new migrant and refugee families and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | To be provided after the scoping phase, in December 2008 |  |  |  |
| Purpose A statement of purpose will be developed in the scoping phase. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.11.1 | Synthesis of literature |  | April 2008 |  | Annotated bibliography completed. |
| 1.11.2 | Scoping paper |  | Dec 2008 |  | Delayed. New milestone date shown, was previously June 2008. See note below regarding ongoing work (next 3 months). |
| Progress to date (previous 3 months work) - Officials from MSD and Office for Ethnic Affairs met to discuss the status and gaps in current knowledge/research on family violence in migrant and refugee families. Some options for possible research projects were discussed. Current ongoing work (next 3 months) - Work has begun on developing a scoping paper setting out options for possible research projects and recommendations for next steps for the Taskforce meeting in December. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 1.12 ELDER ABUSE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Cilla Corlett |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (from work programme) Improve our understanding of the nature of elder abuse and successful models of prevention and intervention. Actions include: - review existing literature - develop a research agenda - link to the Taskforce strategic research agenda for family violence prevention - recommend further action. |  |  |  |  |  |
| Objective deadline |  | Final deadline to be confirmed by October 2008 |  |  |  |
| Purpose/Expected Outcome: Improved decision-making about viable programme and service delivery to eliminate elder abuse and neglect within the family setting. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.12.2 | Develop a research agenda |  | 30 July 2008 |  | Some delay. MSD and Age Concern NZ have drafted a report to the Taskforce with recommended priorities for further action on elder abuse and neglect (with a recommended research agenda included as part of this). This will be taken to the October Taskforce meeting. |
| 1.12.3 | Link to the Taskforce strategic research agenda for family violence prevention |  | Ongoing |  | On track. Although the proposed programme of action on Elder Abuse and Neglect (EAN) will encompass all forms of elder abuse and neglect across all settings, not just within families, strong links will be made between the EAN research agenda and family violence prevention in the above work. |
| 1.12.4 | Recommend further action |  | -May 2008 -21 July 2008 -August 2008 -17 Sep 2008 |  | -Report to Minister seeking approval of a proposed work programme, timeline and governance arrangements for working towards developing a national action plan for elder abuse and neglect. Complete. -Workshop with sector on issues and priorities. Completed -Consultation with sector on issues and priorities. Complete. -Report to Taskforce (for Taskforce October 2008 meeting) with recommended priorities for action. On track. |
| Background The proposed research agenda on Elder Abuse and Neglect is covered in the report to the Taskforce in October 2008 (see below). Progress to date (previous 3 months work) - Workshop with selected group from sector held 21 July 08 - Priorities for further action identified. Current ongoing work (next 3 months) - Report to Taskforce (for Taskforce October 2008 meeting) on work undertaken on elder abuse and neglect to date, with an outline of proposed priorities for further action. Timing / Ongoing / Recommendations / Conclusions Status = On track. Final deadline to be confirmed. |  |  |  |  |  |

| ### 1.13 DATA ON NGO SERVICE DELIVERY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | NGOs, ACC, Justice, Police, Health |  |
| Project Manager |  |  |  | Dorothy Adams |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (from work programme) High quality data available about services delivered by, and on the demand for, NGO and agency family violence services. Actions include: - develop systematic and accurate data on services. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose To understand the family violence services available and the ongoing demand for services – both volume and type. This work is aligned with the “Pathway to Partnership” initiative. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 1.13.1 | Scoping study and project plan. |  | July 2008 |  | On track. A Terms of Reference for investigating the development of a data collection system has been approved by the Pathway to Partnership Management Group. |
| 1.13.2 | Determine reporting and monitoring information requirements, data currently available and data collection methods. |  | 30 Oct 2008 |  | Planning to be completed by 12 September 2008. Analysis to commence September 2008. |
| 1.13.3 | Determine requirements for reporting and evaluation systems support (linked to the Outcomes Framework Project). |  | 15 Dec 2008 |  | Follows data collected in 1.13.2. |
| 1.13.4 | Conduct a monitoring and reporting trial of an information model with NGO and MSD participants. |  | 30 Oct 2008 |  | Information model already being trialled with two MSD initiatives. |
| 1.13.5 | Define the requirements that relate to potential ongoing information management solutions. |  | 15 Dec 2008 |  | Follows data collected in 1.13.2. |
| Background As part of Pathway to Partnership (P2P) initiative, which is aimed at ensuring a sustainable social sector for NGOs providing essential services for families, children and young people, a data monitoring system that focuses on outcome measures will be developed and implemented in collaboration with the sector. This monitoring system will provide high quality data about service outcomes. All essential Family Violence prevention services will be part of this initiative. Current ongoing work (next 3 months) A Terms of Reference for investigating the development of a data collection system has been approved by the Pathway to Partnership Management Group. The key milestones of that work are set out above. Timing / Ongoing / Recommendations / Conclusions Recommend that milestone 1.13.1 be progressed via the milestones agreed for the Monitoring and Evaluation workstream for P2P which are set out in detail in the Terms of Reference with the key milestones set out above. Status = on track. |  |  |  |  |  |

### Changing Attitudes and Behaviour

| ### 2.1 KIA PUAWAI |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development |  |
| Contributors |  |  |  | All Taskforce members |  |
| Project Manager |  |  |  | Anne Riley |  |
| First Programme of Action reference |  |  |  | Not in first Programme of Action |  |
| Objective and actions (as per Work Programme) Kia Puawai supported in its implementation by the Taskforce. Taskforce supports initiatives such as: - increasing coverage of intensive home visiting - providing free Early Childhood Education for all vulnerable children aged 18 months – 3 years - developing an integrated identification, assessment and referral system for young children - expanding Early Years hubs and teen parent co-ordinators initiatives - key workers to support at-risk families - expanding Social Workers in Schools. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose This cross-agency initiative is building an early years intervention system to help ensure all children flourish in early childhood and reach their potential as young adults capable of developing healthy, respectful and violence free relationships throughout their lives. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.1.2 | Progress report delivered to Ministers on results of evaluations of pilot programmes to improve outcomes for children and their families. |  | Nov 08 |  | On track. Evaluations commenced. |
| 2.1.3 | B4School check pilot in place |  | Aug 08 |  | On track. Work underway. |
| Progress to date (previous 3 months work) - Work has continued on evaluating four pilot programmes to improve outcomes for children and their families. This work will inform a report back to Cabinet on future funding decisions. Current ongoing work (next 3 months) - The B4School pilot being progressed by the Ministry of Health is due to be in place in August 2008. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.2 IMPROVING ATTACHMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Health / Auckland District Health Board |  |
| Contributors |  |  | MSD, ACC, Education, NGOs |  |
| Project Manager |  |  | Pat Tuohy / Carol Stott |  |
| First Programme of Action reference |  |  |  |  |
| Objective and actions (as per Work Programme) Promote and improve attachment between new-born babies and parents and care-givers. Actions include: - progress a pilot - see how well it works - report - draw on key findings from parent support and development programmes already focused on supporting attachment between young children and parents and caregivers. |  |  |  |  |
| Objective deadline |  | July 2009 |  |  |
| Purpose Supporting the promotion of healthy secure attachment in infants is important for the development of quality relationships between infants and parents and caregivers, and for its effect on human development and wellbeing. Promotion of secure attachment can be provided through provision of information to parents, and support with strategies that enhance attachment and address any parenting concerns. Early intervention is recommended for infants of high-risk carers if developmental or behavioural problems are detected. |  |  |  |  |
| Key Milestones |  |  | Date | Description of Progress |
| 2.2.1 | Inclusion of an additional visit in the Well Child Framework for first time parents, especially fathers and male partners. |  | July 2009 | Project planning commenced. |
| 2.2.2 | Promotion of infant-parent attachment and assessment of parent /child relationship difficulties in revised Well Child Framework. |  | July 2009 | Project planning commenced. |
| 2.2.3 | Training for Well Child Providers to promote secure infant-parent attachment. |  | July 2009 | Project planning commenced. |
| 2.2.4 | Establishment of a pilot in the Auckland District Health Board area to prevent Shaken Baby Syndrome (head injuries to babies caused by violent shaking). |  | TBC | This pilot has been delayed and the milestone date changed due to issues that arose during scoping. The Ministry is currently working with three Auckland DHBs on the feasibility of this pilot. |
| Background The pilot to prevent Shaken Baby Syndrome (key milestone 2.2.4) did not proceed as initial scoping highlighted issues with the pilot site. Progress to date (previous 3 months work) - Project planning on the implementation of changes to the Well Child Framework has commenced. Current ongoing work (next 3 months) - Funding has been provided for a workshop on understanding and promoting attachment in Auckland, this will be run in October. - The Ministry is conducting a project on developing evidence-informed guidance for District Health Boards on the provision of specialist maternal and infant mental health services in New Zealand (completion date 30 June 2009). The project includes a literature review of best practice in maternal and infant mental health, a key informants group, and the development of guidance documents for DHBs. This work will be aligned with the Well Child programme as part of a continuum of health services for mothers and infants to improve and promote attachment. Timing / Ongoing / Recommendations / Conclusions Status = on track (one key milestone delayed). |  |  |  |  |

| ### 2.3 CONDUCT DISORDER / SEVERE ANTI-SOCIAL BEHAVIOUR |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | Education, Health, Justice and Police (Inter-Agency Plan partners). NGOs, OCC, and other relevant agencies will be consulted on policy development. |  |  |
| Project Manager |  |  | Saskia Patton |  |  |
| First Programme of Action reference |  |  | N/A |  |  |
| Objective and actions (as per Work Programme) Ensure comprehensive behavioural interventions for children aged 3 – 7 years with conduct problems and their families are delivered in accordance with the Inter-agency Plan by building on the specialist behaviours services already provided by the Ministry of Education. In addition, there will be the transitioning of existing services to older children and young people to evidence-based, best-practice interventions. The Taskforce supports the four action areas in the Inter-Agency Plan: - leadership, co-ordination, monitoring and evaluation - transition existing service provision to evidence-based, best-practice interventions - establish an intensive, comprehensive behavioural service for 3 -7 year olds - build a shared infrastructure for the delivery of specialist behavioural services. |  |  |  |  |  |
| Objective deadline |  | 2012 |  |  |  |
| Purpose Developing and delivering a suite of services for the 5% of early childhood and primary (and intermediate) school aged children who have conduct problems will reduce the prevalence of young people with these problems. Without appropriate interventions, these children are more at risk of becoming perpetrators of violence. Over time these services are anticipated to result in a subsequent reduction in cases of family violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.3.1 | Establish experts advisory group |  |  | Mid Nov 2007 | Completed |
| 2.3.2 | Best practice report completed |  |  | June 2008 | Some delay. Draft completed – agreement being sought on sign-off for publication |
| 2.3.3 | Agency service reviews/stocktake completed |  |  | Dec 2008 | On track |
| Background This is an inter-agency project which seeks to improve behavioural interventions for 0-17 year olds across service areas of the Ministries of Education, Health, Justice and Social Development (CYF). In particular, it will establish a comprehensive behavioural service for children aged 3-7 years (subject to further investment) and transition existing services to older children and young people to evidence-based, best-practice interventions. Progress to date (previous 3 months work) - The Advisory Group for Conduct Problems (AGCP) had its first meeting on 14 November 2007 and has met seven times in 2008. - Members of the AGCP met with the Ministers of Health, and Social Development on the Inter-agency Plan for Conduct Disorder/Severe Antisocial Behaviour 2007-2012 and discussed the draft best practice report on the definition, treatment and management of conduct problems in children and young people. - Members of the AGCP have finalised the best practice report which is due to be printed and released in September 2008. - AGCP are currently drafting a second report: Translating Evidence into Practice which is looking at programme selection for 3-7 year olds and a research design to best support the implementation of selected programme(s). - The Maori expert advisory group (Te Roopu Kaitiaki) has also been established to provide comment on responsiveness of ‘generic’ services to Maori consider the parallel development of programmes based in Te Ao Maori. - Agencies continuing to undertake stocktake of current services that may need to be transitioned to evidence-based practice. - Planning for a 2009 budget submission. Current ongoing work (next 3 months) - AGCP will continue drafting the Translating Evidence into Practice report (focus on 3-7 year olds services). - AGCP work programme/ roadmap planning. - Officials and AGCP planning to run a workshop on implementation and transition issues. - MSD will be developing an implementation plan to support the delivery of the Inter-agency Plan. Timeframes on delivery of new services to 3-7 year olds subject to decisions on further investment. - Te Roopu Kaitiaki will be drafting a report reviewing the evidence base and research requirements in considering the development of parallel Te Ao Maori-based services. - 2009 budget-bid information expected to be finalised. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.4 CURRICULUM DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Education |  |  |
| Contributors |  |  | MSD (MYD), Health, TPK, MPIA, OCC, NGOs |  |  |
| Project Manager |  |  | Sue van Daatselaar |  |  |
| First Programme of Action reference |  |  | N/A |  |  |
| Objective and actions (as per Work Programme) Children and young people aged 5-18 years develop the knowledge and skills that they need to support good decision-making, to make healthy choices, and to seek help when they need it. Actions include: - provide support to enable schools to develop their programmes within the New Zealand curriculum to suit the diverse learning needs of their community - strengthen whole-school, strengths-based approaches that promote resilience and confidence in young people and those adults who support them - seek opportunities to identify and respond to children who are affected by family violence. |  |  |  |  |  |
| Objective deadline |  | Ongoing |  |  |  |
| Purpose The purpose of education is to help children and young people reach their potential and develop the competencies they will need to live, learn, work and contribute as active members of their communities. Education contributes to the prevention and reduction of family violence in New Zealand communities by providing a safe environment that teaches and models skills to enable children and young people to manage their own well-being and to relate in healthy ways with others. It provides children and young people with the opportunity to learn skills they might not otherwise receive in the home environment. To experience the benefits of education, students must participate and be engaged with the education system. The Ministry of Education supports educators to identify students who are at risk as a result of experiencing, witnessing or engaging in family violence and to work with parents, families and whänau, and other agencies to ensure these students are appropriately supported. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 2.4.1 | Provide support to enable schools to develop their programmes within the New Zealand curriculum (NZC) to suit the diverse learning needs of their community. - Release final curriculum and supporting resources for schools to support the implementation of the curriculum - Professional leaders are supported to lead curriculum development, establish the conditions for professional learning and involve families/whanau in focusing on student achievement and educational outcomes based on the NZC. |  |  | Ongoing Ongoing | Ongoing. We have released the New Zealand Curriculum (English medium schools) and are continuing work to finalise Te Marautanga o Aotearoa (Māori Medium curriculum), which is planned for release in late 2008. We are continuing to develop resources and information to support the implementation of these curriculum frameworks. Consultation on the position paper ‘Kiwi Leadership for Principals’ has been completed and the document was released on 7 August 2008. |
| 2.4.2 | Strengthen the implementation of whole-school, strengths-based approaches that promote resilience and confidence in children and young people and those adults who support them. - Support up to 730 teachers per year in developing effective teaching and leadership skills to support the implementation of school-wide approaches to student well being / mental health. This involves strengthening teachers’ understanding of the connections between school organisation, curriculum design and delivery and community consultation and partnerships. - Identify successful professional learning approaches for teachers from the evaluation of the student wellbeing contracts and incorporate in the design and delivery of ongoing professional development contracts. |  |  | Ongoing | On 3 July 2008, the Ministry of Education launched a four pronged approach to support school staff, parents and students in preventing bullying in schools. Ongoing. Contracts providing support for up to 730 teachers per year in implementing school-wide approaches to student wellbeing and mental health are in place. The Ministry, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts and to integrate the learning in ongoing professional development contracts. |
| 2.4.3 | Seek opportunities to identify and respond to children and young people who are affected by family violence. - Review the quality and accessibility of support available to educators who are concerned about children and young people affected by family violence. - Develop a review of the support received by children and young people identified while at school as affected by family violence (in conjunction with obj 1.4 Child Maltreatment). |  |  | Ongoing Ongoing | Modifications to the education profile and plan guidelines and templates for children in care have been made as a result of the trial currently underway within the Auckland District Health Board. A broader action plan will be informed by the findings of a review of the contribution that education makes to the prevention of child maltreatment (see obj 1.4 Child Maltreatment). The review has been scoped and a draft project plan developed. |
| Background In 2002, the Ministry of Education’s Curriculum Stocktake Report identified that, while many students were achieving at world-class levels, there are wide disparities in outcomes for diverse students. Progress to date (previous 3 months work) 2.4.1 The New Zealand Curriculum The second report on the exploratory studies of ‘early adopters’ of the New Zealand Curriculum (NZC) has been received and we are currently planning for these exemplars to be written for publication by early 2009. The document for Te Marautanga o Aotearoa (Mäori Medium curriculum) will be finalised and released in late 2008. The final document Kiwi Leadership for Principals (KLP) was released on 7 August. KLP presents a model of leadership that reflects the qualities, knowledge and skills required to lead New Zealand schools from the present to the future. KLP will be used as a reference point for developing the Professional Leadership Strategy. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people The Ministry of Education launched the four pronged approach to bullying initiatives on 3 July 2008, which includes resources and information for students, parents, teachers and principals. New resources included the “Step up, Be Safe” pocket card resource, written for students by students. There are two versions, one for primary and one for secondary. ERO will be asking schools whether incidents of particular types of bullying have occurred in their school and what policies and programmes have been developed to combat bullying. The Ministry, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts. The use of the resources on bullying and the drug education matrix are being promoted through this programme. 2.4.3 Identifying and referring children affected by family violence to appropriate services Modifications to the education profile and plan guidelines and template for children in care have been made as a result of the trial currently underway within the Auckland District Health Board. The Taskforce has agreed to include a review of the education sector’s contribution to child maltreatment prevention as part of Obj 1.4. The scope and project plan have been finalised by the Ministry of Education and will be implemented over 2008/09. Current ongoing work (next 3 months) 2.4.1 The New Zealand Curriculum We will be organising for the findings from the exploratory studies of ‘early adopters’ of the New Zealand Curriculum (NZC) to be written into exemplars for publication in early 2009. Consultation with schools, whänau, hapu, iwi and community groups is helping to scope the development of appropriate resources needed to implement Te Marautanga o Aotearoa (Mäori medium curriculum) following its release. This work will continue through until 2010. We are now working on the Principals’ Leadership Strategy, which is planned for release in February 2009. This strategy will provide a three to five year plan outlining how the Government intends to work with the sector to achieve the goal of strong professional leadership in every New Zealand school by 2012. 2.4.2 Whole-school, strengths-based approaches that promote resilience and confidence in children and young people We will continue to develop a resource called Making a Difference which will show how eight New Zealand schools are engaging students in positive learning and achievement. We will continue to update and promote the supporting positive behaviours website. The Ministry, the national coordinator and facilitators are continuing to review and improve the models used in the delivery of the Student Well-Being and Mental Health contracts. 2.4.3 Identifying and referring children affected by family violence The trial of the education profile and plan will be extended to Counties Manakau, Wairarapa, Horowhenua and Lakes District. The project plan to review of the education sector’s contribution to child maltreatment prevention will be implemented. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.5 VIOLENCE IN THE MEDIA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Radha Balakrishnan |  |
| First Programme of Action reference |  |  |  | Action 23 |  |
| Objective and actions (as per Work Programme) Create awareness of impact of violence in the media on children aged between 6 to 11 years. Actions include: - scope an evidence-based public education and awareness programme aimed at parents - scope financial implications - develop an implementation plan. |  |  |  |  |  |
| Objective deadline |  | February 2009 |  |  |  |
| Purpose To scope a public education and awareness programme around violence in the media (its risks and impact) with an initial focus on parents of 6-11 year olds. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.5.1 | Convene Advisory Group |  | Aug 2008 |  | It has been agreed that the best way to progress this work is to consult with key agencies to develop the plan rather than establishing a specialist advisory group. |
| 2.5.2 | Develop plan |  | Oct 2008 |  | Not commenced |
| 2.5.3 | Draft Report circulated for comment |  | Dec 2008 |  | Not commenced |
| 2.5.4 | Report to the Taskforce |  | Feb 2009 |  | Not commenced |
| Background Violence in the media and its impact on society generally was raised at the meeting with the Family Violence Ministerial Team and with members of the Multi-Party Working Group on Family Violence, when the Taskforce’s First Report was presented in mid 2007. The first programme of action included an action to review how violence is portrayed in the media and in particular the 2004 Report on TV Violence in New Zealand, and advise on implications for the next Programme of Action. The Families Commission agreed to lead this work. The Taskforce supported raising awareness of the impact of violence within the media on children and young people. The 2004 report identified middle childhood (between 6-11 years) as a vulnerable group and it was agreed that this group should be the initial focus of any public education work. Progress to date (previous 3 months work) - There have not been any major developments on this project in the last three months. - The Broadcasting Standards Authority has recently released a report - Seen and Heard: Children’s Media Use, Exposure, and Response. The focus of the research was how New Zealand children use and respond to television, radio, the internet, and cellphones. Current ongoing work (next 3 months) - Early discussions have occurred with interested agencies. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.6 CAMPAIGN FOR ACTION ON FAMILY VIOLENCE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | MSD / Families Commission |  |
| Contributors |  |  |  | NGOs |  |
| Project Manager |  |  |  | Gael Surgenor |  |
| First Programme of Action reference |  |  |  | Actions 29-39 |  |
| Objective and actions (as per Work Programme) Continue the Campaign for Action on Family Violence through: - an advertising campaign - resource development and distribution - Community Action Fund projects. |  |  |  |  |  |
| Objective deadline |  | 30 June 2009 (Ongoing to 2010) |  |  |  |
| Purpose This is a community-based social marketing campaign which aims to influence the behaviour of target audiences, including perpetrators of family violence and their influencers. The programme is based on research into attitudes and towards family violence and motivators and barriers to behaviour change. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.6.5 | Administering two further rounds of the Community Action Fund to support local projects to support change at a local level. Mid 2008 and early 2009. |  | August 2008 Early 2009 |  | Round three of the Community Action Fund closed on 10 June and 35 successful applicants were announced early August. A fourth round is confirmed for early 2009. |
| 2.6.6 | Continue to support the messages of the television campaign during 2008/09 using the website, the 0800 information line and print resources. |  | June 2009 |  | The 0800 telephone line continues to provide information and support to over 600 callers per month. The television advertisements are having a sustained impact on website visit numbers and remain at over 8,000 visits per month from June through to August. New resources will be developed depending on the development of the next phase of the campaign which is currently being scoped – and could focus on child maltreatment. |
| 2.6.7 | Continue a television advertising campaign addressing attitudes to family violence and intimate partners violence during 2008/09 – 5 weeks of advertising to be run. |  | 12 June 2009 |  | A further five weeks are booked for late July, August, September, December and January |
| 2.6.8 | Continue to build on the media advocacy work with the national news media to promote more responsible coverage of stories of family violence and provide training and support to enable community spokespeople to engage effectively with local media |  | 12 June 2009 |  | Media workshops delivered in Taupo, Rodney and Feilding/Kapiti and more booked for Wanganui, Dunedin and Rotorua. Age Concern Auckland and Police Family Violence Coordinators are also booked for the media workshop. |
| 2.6.9 | Continue to identify and encourage campaign ‘champions’ and spokespeople, to develop partnerships in business, sport and youth related organisations and to continue to seek opportunities for promotion within popular culture. |  | 12 June 2009 |  | The New Zealand Breakers basketball is adopting the campaign. Porirua City Council and Hamilton City Council are planning to localise the campaign. Actors Annie Whittle and Tammy Davis are speaking out in women’s magazines in support of campaign. |
| 2.6.10 | Continue to measure the level of public awareness of the key messages of the Changing Attitudes and Behaviours Campaign |  | 30 June 2009 |  | The reach and retention survey will continue throughout 2008/09 year. Two sets of reach and retention survey results released so far show that the campaign has been extremely effective to date. |
| Background All key milestones were met for the objective deadline of June 2008. A new deadline (30 June 2009) has been inserted above for the work taking place in 2008/2009. The Campaign for Action on Family Violence (the campaign) is a four year campaign that calls on everyone to help put an end to family violence in New Zealand. The national campaign was launched with TV advertisements in September 2007. The campaign message “Family violence – It’s not OK” has struck a chord with New Zealanders and has quickly become part of the kiwi vernacular. The campaign is supported by a website, an 0800 Information Line and a Community Action Fund that provides financial support for community-led activities. Progress to date (previous 3 months work) - Resources continue to be distributed and the 0800 telephone line continues to provide information and support. - The campaign’s media advocacy work is continuing. - Advertisements from the first and second phase of the campaign have been screening at various times in June, July and August. - A third and fourth round of the Community Action Fund have been agreed, with round three closing on 10 June. - 35 successful applicants for the third round of the Community Action Fund were announced in August. Current ongoing work (next 3 months) - Additional weeks of the phase two adverts are going to air in September, December and January 2009. - A third survey into the reach and retention of the TV advertisements will be conducted in September 2008 - Results of a nationwide face to face survey that will specifically explore attitudes about violence towards women, inter-partner violence, and child abuse will be available in October 2008. - A community study is underway that will provide an in-depth analysis of the impact of the campaign. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 2.7 FAMILY VIOLENCE DEATH REVIEW PROJECT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Health |  |
| Contributors |  |  |  | MSD, Justice, Police, NGOs |  |
| Project Manager |  |  |  | Tanith Robb |  |
| First Programme of Action reference |  |  |  | Action 42 |  |
| Objective and actions (as per Work Programme) To establish the Family Violence Death Review Committee. |  |  |  |  |  |
| Objective deadline |  | 31 June 2008 - Complete |  |  |  |
| Purpose The Family Violence Death Review Committee is being established to understand why family violence deaths occur and to enable changes to systems and practices that may contribute to the prevention of future deaths. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 2.7.1 | Undertake consultation on draft Terms of Reference |  | 29 Feb 2008 |  | Completed |
| 2.7.2 | Finalise Terms of Reference and seek Ministerial sign-off |  | 31 Mar 2008 |  | Completed |
| 2.7.3 | Seek nominations for the inaugural members of the Committee |  | 31 Mar 2008 |  | Completed |
| 2.7.4 | Undertake Cabinet appointments process |  | 20 June 2008 |  | Completed |
| 2.7.5 | Appoint members to the Committee |  | 31 June 2008 |  | Completed |
| 2.7.6 | Establish Committee |  | 31 June 2008 |  | Completed |
| 2.7.7 | Induction and first meeting of the Committee |  | By 30 Oct 2008 |  | On track |
| Background In 2006, the Ministry of Health established a cross-agency Family Violence Death Review Project in close collaboration with the MSD, the MoJ, the Police and other key government and non-government organisations. The MoH reported to the Taskforce on 30 June 2007 and recommended that a formal mechanism for an interagency, multidisciplinary family violence-related death review system be established under the New Zealand Public Health and Disability Act 2000 (the NZPHD Act). The family violence death review system proposed involves the establishment of a ministerial committee that is parallel to, but separate from, the current mortality review committees mandated under the NZPHD Act. The Taskforce agreed to the recommendations in the report. Progress to date (previous 3 months work) - The inaugural members were appointed to the Family Violence Death Review Committee (FVDRC) by Hon Steve Chadwick, for Hon David Cunliffe, on 6 August 2008. The members are as follows: - Wendy Davis (Chairperson) - Ngaroma Grant - Brenda Hynes - Dr Patrick Kelly - George Ririnui - Dr Alison Towns - Rob Veale - Vaoga Mary Watts. Current ongoing work (next 3 months) - The FVDRC’s induction day will be on 1 October and the Committee will hold its first meeting on 2 October 2008. Timing / Ongoing / Recommendations / Conclusions Status = Completed. The Family Violence Death Review Committee has been established and appointed. Work of the Family Violence Death Review Committee is now Ministry of Health business as usual, and will be reported on internally. The purpose of the Committee is set out in Terms of Reference, the Committee will report to the Minister of Health annually. The Secretariat for the FVDRC is Ms Aphra Green at the Ministry of Health. |  |  |  |  |  |

### Ensuring Safety and Accountability

| ### 3.1 FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs |  |
| Taskforce Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Karyn McLean/Dominic Lepa |  |
| First Programme of Action reference |  |  |  | Action 56 |  |
| Objective and actions (as per Work Programme) Two new Family Violence Courts established. Actions include: - project planning - identification of locations - stakeholder consultation - implementation. |  |  |  |  |  |
| Objective deadline |  | A variation is being sought to extend this deadline to early 2009 |  |  |  |
| Purpose To ensure all parties are prepared ahead of the implementation to support new Family Violence Courts being established. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.1.1 | Project planning for implementation and establishment of two new Family Violence Courts |  | June 2008 |  | Completed. High level project planning has been completed. The Chief District Court Judge has confirmed Palmerston North (12 September 2008) and Whangarei (date tbc, likely to be April 2009) as the locations for the new Family Violence Courts. More detailed project planning is now underway. A variation was sought in July 2008 regarding the opening of the Whangarei Court moving to April 2009. |
| 3.1.2 | Identification of locations |  | June 2008 |  | Completed. Confirmed as Palmerston North and Whangarei. |
| 3.1.3 | Stakeholder consultation |  | Sept 2008 |  | Date changed, reflected in approved variation. Consultation has occurred with defence counsel, Police, Corrections, the Judiciary, staff and key NGOs for the Palmerston North Court. A meeting is being held 5 September with all key stakeholders to finalise procedures before the opening on 12 September. A variation has been approved to allow for the new timeframe for the Whangarei Family Violence Court opening in 2009. |
| 3.1.4 | Communications strategy |  | Early 2009 |  | A variation was sought in July 2008 to delay the communications strategy to allow for the implementation of new courts. This variation was approved. |
| 3.1.5 | Implementation of two new Family Violence Courts |  | April 2009 |  | A variation was sought in July 2008 regarding the opening of the Whangarei Court moving to April 2009 and Palmerston North to September 2008. The variation has been approved. The Palmerston North Family Violence Court will open on 12 September 2008. |
| Progress to date (previous 3 months work) The Chief District Court Judge has confirmed Palmerston North and Whangarei as the locations for the new Family Violence Courts. Palmerston North will be implemented in September 2008 and Whangarei to follow, likely to be in April 2009. Staff/stakeholder training and consultation has been completed for the Palmerston North Family Violence Court. Current ongoing work (next 3 months) The Palmerston North Family Violence Court opens on 12 September 2008. A meeting with key stakeholders is occurring on 5 September to finalise procedures for the Court opening. Over the next three months the Ministry of Justice will be monitoring how the roll out of the Court is progressing. Planning for the opening of the Whangarei Family Violence Court in early 2009 continues. Timing / Ongoing / Recommendations / Conclusions Status = Opening of the Palmerston North Family Violence Court is on track. A variation has been approved to accommodate the new timeframes for the Whangarei Family Violence Court. |  |  |  |  |  |

| ### 3.2 PROTOCOLS FOR FAMILY VIOLENCE COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Judiciary / Ministry of Justice |  |
| Contributors |  |  |  | Police, NGOs. |  |
| Liaison |  |  |  | Justine Cornwall |  |
| Project Manager |  |  |  | Karyn McLean/Dominic Lepa |  |
| First Programme of Action reference |  |  |  | Action 57, 58 |  |
| Objective and actions (as per Work Programme) A national protocol for improving how Family Violence courts are established and run. Actions include: - develop protocols - stakeholder consultation - implementation. |  |  |  |  |  |
| Objective deadline |  | August 2008 |  |  |  |
| Purpose The purpose of this protocol will be to: - outline the requirements of key staff involved in Family Violence Courts - outline key areas of best practice to ensure there is consistency across all Family Violence Courts. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.2.1 | Development of Operating Guidelines to ensure consistency across all Family Violence Courts |  | 21 Dec 2007 |  | Completed. Released as below. |
| 3.2.3 | Approval and distribution of Operating Guidelines across all Family Violence Courts |  | August 08 |  | Completed. Incorporation of feedback and final consultation completed in August. The guidelines were approved on 1 September and were issued to Family Violence Court staff on 8 September 2008. Key stakeholders that contributed to the development of the guidelines also received a copy. The guidelines are available on the Ministry of Justice website. |
| 3.2.4 | Communications strategy |  | August 08 |  | Completed. A communications strategy has been developed to coincide with the distribution of the Guidelines. |
| Progress to date (previous 3 months work) Consultation on the National Operating Guidelines for Family Violence Courts is complete. The Guidelines have been endorsed by the Chief District Court Judge and approved by the Ministry of Justice. The Guidelines were issued to staff on 8 September 2008. The guidelines were also provided to key stakeholders for their information. The guidelines are available on the Ministry of Justice website. Timing / Ongoing / Recommendations / Conclusions Status = Objective completed. The guidelines will be updated as and when required, reflecting any policy or legislative changes. For example the guidelines will be updated to incorporate the Independent Victim Advocate role that will be introduced in April 2009. |  |  |  |  |  |

| ### 3.3 SOCIAL SERVICES SUPPORTING COURTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | Ministry of Social Development / Ministry of Justice |  |
| Contributors |  |  |  | Police, MWA, NGOs, ACC |  |
| Project Manager |  |  |  | Ann Riley / Justine Cornwall |  |
| First Programme of Action reference |  |  |  | Action 52 |  |
| Objective and actions (as per Work Programme) A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. Actions include: - introduction of Independent Victim Advocate / support person role in all Family Violence Courts - introduce specialist enhanced case management staff in all Family Violence Courts - referral and funding for non-mandated stopping violence programme providers for offenders. |  |  |  |  |  |
| Objective deadline |  | April 2009 |  |  |  |
| Purpose A social services system modelled around family violence courts to support the courts by linking services to ensure victims and observers are kept safe, perpetrators are kept accountable and responsible, and families are assisted with their recovery needs. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 3.3.1 | Project plan with ongoing milestones and agency roles completed |  | April 2008 |  | Complete. MoJ and MSD meet regularly to monitor the progress of this project. |
| 3.3.2 | Scoping and developing Independent Victim Advocate (IVA). |  | Oct 2008 |  | Scoping and development of the Independent Victim Advocate role is underway. Consultation with NGOs, Judiciary, and key stakeholders will be completed by the end of September with a view to finalising the role by the beginning of October (milestone date adapted to reflect this date). MSD will start recruiting for the provider to recruit and train the 8 Independent Advocate roles by January 2009. |
| 3.3.3 | Introduce specialist enhanced case management staff in all Family Violence Courts (FVCs) |  | TBC |  | There has been a delay in this work. MoJ is currently assessing other funding streams to fund this initiative. This work is ongoing. No completion date confirmed. |
| 3.3.4 | Referral and funding for non-mandated stopping violence programme providers for offenders |  | July 2008 |  | Complete. |
| 3.3.5 | Consultation with other agencies and non-government organisations on the development of the role of the independent victim advocate/support person. |  | Aug/Sept 2008 |  | The Ministry of Justice has begun consulting internally and with Police and MSD. A workshop was held in early August with NGOs and external government agencies. From this consultation a draft role description has been developed and the Judiciary has been consulted on this draft. Further work has been undertaken on the role description and consultation with NGOs and external government agencies on the draft role description will be undertaken in September. |
| 3.3.6 | The advocate/support person role will be rolled out in FVCs. |  | From 1 April 2009. |  | On track |
| Background A variation to this objective was approved by the Chair of the Taskforce on 4 April 2008. The variation was sought because the previous deliverables and milestones did not align with the direction the Chief District Court Judge has set for the Family Violence Courts (FVCs). The Government has announced that it will move towards fully funding actions 1 and 3 of this objective from 2008/2009 (Introduction of Independent Victim Advocate/support person role in all FVCs, and referral and funding for non-mandated stopping violence programme providers for offenders). Progress to date (previous 3 months work) - The Project Plan and Terms of Reference for this objective have been finalised and agreed. - The Ministry of Justice has begun work on developing the role of an independent victim advocate / support person to provide support and assistance to victims of domestic violence in the FVCs in conjunction with the MSD. - Consultation with other agencies and non-government organisations took place in August 2008. The Ministry of Justice has begun consulting internally and with Police and other major stakeholders. Workshops were run over two days with input from NGOs and relevant agencies. A meeting was held with the Chief Family Court Judge on Tuesday 2 September to discuss the Judiciary’s feedback on the draft role description for the Independent Victim Advocate role. - The role description for the Independent Victim Advocate role will be completed and signed off by the end of September/early October. Current ongoing work (next 3 months) - The management of the selection process, including preparing documentation, for the provider(s) that will recruit and train the 8 Independent Victim Advocates Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

### Effective Support Services

| ### 4.1 MAORI SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | TPK, NGOs, Education |  |  |
| Project Manager |  |  | Ann Dysart |  |  |
| First Programme of Action reference |  |  | Action 7 |  |  |
| Objective and actions (as per Work Programme) Maori Service Workforce Development. Actions include: - 60 Maori trained to work with the Mauriora framework. - Ongoing support of trained practitioners. |  |  |  |  |  |
| Objective deadline |  | June 2009 |  |  |  |
| Purpose This proposal will allow for continued investment in the training and support of practitioners who work with Maori whanau/communities where there is violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.1.6 | Ongoing assessment and further training, including assisting Mauri Ora practitioners to meet annual licensing and supervision requirements (follows 4.1.3). |  |  | Dec 2008 | A further range of training is currently being contracted to maintain levels of supervision and facilitation training. |
| 4.1.7 | Training modules completed (follows 4.1.4). |  |  | Nov 2008 | On track |
| 4.1.8 | Development of supervision systems (follows 4.1.5). |  |  | Dec 2008 | Underway, appropriate people selected for training. |
| Progress to date (previous 3 months work) - All Mauri Ora training complete. - Further development of a range of DVD of key Maori leaders giving messages around the kaupapa of family violence. - New resources are being developed. Current ongoing work (next 3 months) - With funding now on a continuing basis the negotiations are underway for the next round of training. - The Provider is currently working with Te Kaiawhina Ahumahi to progress the recognition of learning provided. It is envisaged that students will eventually be able to cross credit Mauri Ora Training to a Diploma of Social Work. Timing / Ongoing / Recommendations / Conclusions Status = First phase complete to June 2008. Further reporting deadline of June 2009 for ongoing support and development of practitioners. |  |  |  |  |  |

| ### 4.2 PACIFIC SERVICE WORKFORCE DEVELOPMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | MPIA, NGOs, Education |  |  |
| Project Manager |  |  | Richard Joblin |  |  |
| First Programme of Action reference |  |  | Action 7 |  |  |
| Objective and actions (as per Work Programme) Variation submitted to adjust Objective, awaiting approval. Pacific Service Workforce Development. Actions include: - preparation of a project plan to guide workforce training and development in family violence services for Pacific families. |  |  |  |  |  |
| Objective deadline |  | July 2008 (Variation submitted to change deadline, awaiting approval) |  |  |  |
| Purpose This work plans to increase the quality and diversity of services working to eliminate family violence in the Pacific communities. This will include identifying the capacity and capability of this workforce and the avenues needed to further build and support Pacific People in working to stop family violence in Pacific Families. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.2.1 | Project plan developed under Pathway to Partnership to address building provider workforce capability and capacity. This will include the development of the Pacific workforce. |  |  | TBC | This work is now incorporated under the Pathway to Partnership plan. On 8 August the Minister for Social Development considered a report on strengthening collaborative action under Pathway to Partnership. The Minister agreed to a longer-term investment approach to provider capability building being developed by March 2009 and that contracts for provider development funding will be reviewed for consistency with this approach as they come up for renewal. |
| Background This work is now incorporated within the Pathway to Partnership (P2P) plan. On 12 February 2008, the Government announced an additional funding package for the P2P plan worth $446 million, to be phased in over the next four years. Pacific service workforce development is incorporated under the work-stream to address providers’ ability to build workforce capability and capacity. A steering group for the P2P plan has overseen the development of P2P over the last year. A representative from the PAG is on this steering group. Current ongoing work (next 3 months) - The P2P workforce and provider development project plan is currently being clarified. A variation to this objective has been submitted. Timing / Ongoing / Recommendations / Conclusions Status = delayed. Variation submitted July 2008, awaiting approval. |  |  |  |  |  |

| ### 4.3 SERVICE DEMAND DATA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  | Ministry of Social Development |  |  |
| Contributors |  |  | NGOs, Justice, Health, ACC, Police |  |  |
| Project Manager |  |  | Dorothy Adams |  |  |
| First Programme of Action reference |  |  |  |  |  |
| Objective and actions (as per Work Programme) Monitor increases in demand for family violence services resulting from the Campaign to create sustainable responses to increased demand. Actions include: - develop monitoring framework - create a system response mechanism. |  |  |  |  |  |
| Objective deadline |  | October 2008 |  |  |  |
| Purpose To identify changes in service demand associated with the roll out of the Campaign for Action on Family Violence. |  |  |  |  |  |
| Key Milestones |  |  |  | Date | Description of Progress |
| 4.3.2 | Repeat quantitative measures as above. |  |  | June 2008 | Completed |
| 4.3.3 | Triangulation of quantitative data from qualitative field work. |  |  | October 2008 | Underway |
| Background Monitoring systems were developed to measure the initial impact in service demand associated with the Campaign for Action on Family Violence. These monitoring systems included data from the 0800 number, CYF and Police. The quantitative measures included in these monitors will be repeated. Qualitative data collected from the NGO sector in selected communities will compliment the quantitative monitors. The qualitative data collection will focus on the contribution that the Campaign for Action on Family Violence has had on any change in service demand experienced by the NGO sector since the commencement of the Campaign. Progress to date (previous 3 months work) - Scoping of available administrative data from MSD, Police, and NGOs to measure impact on service demand underway. - Draft monitoring framework and report developed. - Qualitative data collection has commenced with NGOs in three communities (Porirua, Gisborne and Christchurch) to understand whether any changes in service demand have been observed since the commencement of the Campaign for Action on Family Violence. Current ongoing work (next 3 months) - Qualitative and quantitative data will be analysed to provide information on changes in service demand associated with the roll out of the Campaign for Action on Family Violence. - A report on service demand trends will be fed back to key service lines. Timing / Ongoing / Recommendations / Conclusions Status = on track. |  |  |  |  |  |

| ### 4.4a TRAINING OUR STAFF NB: there are only some agencies for whom it is relevant to complete a training project plan. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | ACC |  |
| Contributors |  |  |  | All agencies |  |
| Project Manager |  |  |  | Refer to objective 1.5b |  |
| First Programme of Action reference |  |  |  | Refer to objective 1.5b |  |
| Objective and actions (as per Work Programme) Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: - assess available training options - develop training that meets organisational needs - plan and implement. |  |  |  |  |  |
| Objective deadline |  | Refer to objective 1.5b |  |  |  |
| Purpose To ensure frontline ACC staff are equipped with the skills and tools to respond to victims, spectators or perpetrators of Family Violence whether they be staff, clients of ACC or members of the communities in which ACC staff belong. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 4.4.1 | Frontline staff skills developed |  | 31 Mar 2009 |  | Following the pilot of two training providers it has been agreed that facilitated training does not meet the needs of ACC’s staff and workforce. Work is now underway to investigate an appropriate alternative. The milestone date has been revised to show a new deadline. |
| 4.4.2 | Establishment of specialist family violence support people |  | 31 July 2008 |  | Complete. External support package in place via partnership with Stratos. |
| 4.4.3 | Training plan developed for all staff |  | 31 Mar 2009 |  | Modular based training identified as best solution is being investigated following feedback from staff stakeholders. Refer 4.4.1. Milestone revised. |
| This objective relates directly to Objective 1.5b – Family Violence Free Workplaces (FVFW). Ongoing work - Work continuing to identify training options and best fit approach – limited success on finding successful programme to date – 3 options trialled and considered, now looking at international research and progress in this space. |  |  |  |  |  |

| ### 4.4b TRAINING OUR STAFF |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Lead agency |  |  |  | CYF |  |
| Contributors |  |  |  | All agencies |  |
| Project Manager |  |  |  | MSD contact – Gerard Bloomfield |  |
| First Programme of Action reference |  |  |  | N/A |  |
| Objective and actions (as per Work Programme) Taskforce agencies at the point of contact with communities are enabled to respond to victims, observers and perpetrators effectively and safely. Actions include: - assess available training options - develop training that meets organisational needs - plan and implement. |  |  |  |  |  |
| Objective deadline |  | Business as usual |  |  |  |
| Purpose To ensure that frontline social work staff are able to recognise and respond to the dynamics present in situations of family violence. |  |  |  |  |  |
| Key Milestones |  |  | Date |  | Description of Progress |
| 4.4.1 | Where identified as part of their professional development plan, frontline social work staff attend a Family Violence workshop. |  | As scheduled in training calendar |  | Business as usual. The workshop is being reviewed as part of an ongoing quality assurance process and will be available as part of the specialists stream within the new Practice Induction programme. |
| 4.4.2 | Family Violence is discussed in numerous other parts of the new Practice Induction in the workplace learning modules, the classroom based two week Practice Foundation and various learning forums that are part of the new Practice Induction programme. |  | As scheduled in training calendar |  | Ongoing. |
| Ongoing work - No change to previous update (July 2008). Business as usual. Timing / Ongoing / Recommendations / Conclusions Status = business as usual. As this Objective is now business as usual and will reported on internally, this project plan will not be included in future reports. |  |  |  |  |  |

# First Programme of Action update

Summary Analysis

The Taskforce for Action on Violence within Families’ (the Taskforce) first programme of action initially consisted of 76 actions which were developed from the Taskforce’s First Report. This was consolidated to 53 actions.

Of these, 26 are complete. Work has commenced on another 18 actions and these are now either ongoing, business as usual, or are annual events. The remaining actions have been subsumed into the Ongoing Programme of Action and, along with other ongoing work, are now reported on and monitored through the regular Monitoring Reports provided to every Taskforce meeting.

Key to ‘Status’

Complete = Action complete. May have informed development of work in Ongoing Programme of Action.

OPOA = Work in these actions has been incorporated into the Ongoing Programme of Action, refer to objective number.

Ongoing or Annual = Initial stage complete, currently Ongoing or business as usual. Some are Annual occurrences.

| # | Action | Agency | Information | OPOA # | Status |
| --- | --- | --- | --- | --- | --- |
| Leadership |  |  |  |  |  |
| 1 | Developing the next Programme of Action (POA) | All TF | OPOA released Feb 2008 | 1.1 | Complete |
| 3 | Successful implementation of POA | All TF | Incorporated into OPOA | 1.1 & 1.1a | Complete, ongoing reporting |
| 7 | Drawing on Maori and Pacific advisory groups | MSD | Representatives on TF, ongoing MRG and PAG meetings advise the TF. | Led to 1.2, 1.3, 1.6, 1.9, 1.10, 2.4, 4.1, 4.2 | OPOA |
| 8 | Incorporating migrant and refugee perspectives | MSD | Informed OPOA | 1.11 | OPOA |
| 9 | Aligning business planning to reflect Taskforce vision | Sec. | Next round of SOIs (2008/2009) to be monitored. | 1.1 | Annual Ongoing |
| 12 | Maintain overview of government strategies to ensure goals and activities are complementary with our work | All TF | Business as usual. Secretariat watching brief to ensure TF are aware of all relevant govt strategies. All TF agencies info share on new strategies, and maintain overview of relevant govt strategies. Also links to other actions. | 2.1 2.3 | Complete to date, Ongoing |
| 13 | Family Violence research strategy | FC | Initial report provided Oct 2007, gaps analysis and other areas where work needed. Discussion doc sent early 2008 on topic priority – ongoing work being done through 2008 in consultation with other research agendas. | Informs 1.9-1.12 Led to 1.13 NGO data | Ongoing |
| 14 | Monitoring the level of family violence in NZ | FC | Refer to Research Strategy | Led to 1.13 & 1.7 | Ongoing |
| 15 | Horizontal learning | MSD | Incorporated into OPOA, Ongoing | 1.7 | OPOA |
| 19 | Evaluate the first POA | MSD | Workshop April 2007. Remaining ongoing actions from POA will be monitored through regular Monitoring Reports. | 1.1a | Complete |
| 21 | Families Commission research programme | FC | 3 year research complete 21a Improving Family Violence surveillance data 21b Elder abuse and neglect research – released Feb 2008 | Informed OPOA | Complete |
| 22 | ACC research programme | ACC | 22a Sensitive claims 22b Effectiveness evaluation 22c Whanau Ora research - extended to mid 2008 22d Evidence based guidelines. |  | Complete 22c only is Ongoing |
| Changing attitudes and behaviour |  |  |  |  |  |
| 23 | Review violence in media | FC | Informed development of 2.5 | 2.5 | Complete |
| 29 | Using research to guide Campaign strategy | MSD | The Campaign continues to 2010, with further development being guided by research and evaluation | 2.6 | OPOA |
| 35 | Campaign strategy | MSD / FC | As above | 2.6 | OPOA |
| 36 | Mass media campaign | MSD / FC | Phase one started Sept 2007, Phase two started Feb 2008. Both phase adverts to be repeated in 2008 and early 2009. | 2.6 | OPOA |
| 37 | Nurturing leaders… | MSD | Business as usual. Identified (and funded) through the Community Action Fund. | 2.6 | OPOA |
| 38 | Partnerships with NGOs | MSD/ FC | NGO groups are contracted to be funded for local initiatives. | P2P | Ongoing |
| 39 | Community Action Fund | MSD | 62 initiatives funded in first two rounds. Successful applicants for third round announced August 2008. 35 projects funded | 2.6 | OPOA |
| 40 | Building knowledge – media advocacy etc | MSD/ FC | 40a media advocacy - FACS 40b FV awareness training – also led to 1.5 40c Toolkit re-released 40d White Ribbon day | 2.6 2.6 1.5 2.6 - | OPOA Ongoing Ongoing Complete Annual |
| 4142 | Family violence death reviews | MoH | Appointments made in August 2008. | 2.7 | OPOA |
| Ensuring Safety and Accountability |  |  |  |  |  |
| 43 | Sharing information in a way that promotes safety and wellbeing | Previously MoJ | The Law Commission and the Privacy Commissioner are exploring approaches to the issue of government information sharing. The Law Commission will release an issues paper in the first half of 2009. |  | Initial work complete, Ongoing |
| 44 | Family Violence victims know what support and services are available | MoJ | New comms material developed and distributed at end 2007/early 2008. Available on Family Court website. |  | Complete |
| 45 | Maximising safety factors when managing court rosters | MoJ | Security policy complete, and was sent to all courts as a circular on 1 April 2008. |  | Complete |
| 46 | Increased thresholds for legal aid eligibility | MoJ | Thresholds increased. Legal aid regulations in force from Mar 2007. |  | Complete |
| 47 | Begin a review of legal aid remuneration rates | LSA | Review complete. Changes recommended. Budget 2008 approves 10% increase for 2008/2009. |  | Complete |
| 48 | Improving information courts provide about legal aid | MoJ | Info updated and provided in court info packs and in DV packs, Dec 2007. Court staff also provided with info for public enquiries. |  | Complete |
| 49 | Testing fixed fees for legal aid | MoJ / LSA | Testing complete. Three things were tested – fixed fees, the removal of prior approval requirements for standard family grants and proforma invoices. It has been decided to proceed with the removal of prior approval and to implement that in October 2008 alongside revised family steps and disbursements. Fixed fees and proforma invoices are on hold. |  | Complete |
| 50 | Building safe and effective programmes for couples and families | MSD / MoJ | Service specifications set. MoJ in consultation with NZ Assoc of Counsellors, timeframes to be set. |  | Ongoing |
| 51 | Build capacity of interpreters in Courts | MSD / MoJ | More interpreters available in courts. Business as usual to continue building availability. |  | Complete |
| 52 | Investigate introduction of advocates in courts | MWA / MoJ / MSD | Investigation completed by MWA. Refer OPOA Objective 3.3 | 3.3 | Complete |
| 53 | Enhanced ability for courts to contact victims directly | MoJ / Police | Already possible, MoJ and Police will continue improving standardised process for CSV1 compliance and referral. |  | Complete |
| 54 | Review purchasing plans for programmes | MoJ | 2008 tender round complete. |  | Complete |
| 55 | Improve process for prosecutions for non-attendance at programmes | MoJ / Police | Memorandum of understanding between MoJ and Police for the transfer of prosecutions to Police signed. Transfer completed in June 2008. |  | Complete |
| 56 | Establish four additional Family Violence Courts | Judiciary / MoJ | Four established. Two further to be established in 2008/early 2009 in Palmerston North and Whanagrei. | 3.1 | Complete |
| 57 | Family Violence Courts Evaluation | MoJ | Waitakere and Manukau evaluation complete. Released August 2008. | 3.2 | Complete |
| 58 | Forum to identify best practice for information exchange | MoJ | Held March 2007. Best practice ideas generated informed development of guidelines by agencies. |  | Complete |
| 60 | Enforcement of protection orders (POs) – police training, performance measures and policies | Police | Initiatives on addressing family violence “big picture” (which include PO’s) complete. Ongoing work continuing. 60a Training 60b Performance measures 60c National investigation and prosecution policies. Protection Orders research response also monitors this work, next report due to Minister end Sept 2008. | Many & 4.4 | Many initiatives complete, Ongoing work |
| 61 | Support and training for lawyers working in family violence-related areas | Judge Boshier | Workshops for FC lawyers done in 2007, Law Soc also produced a resource booklet. Similar training is likely to be ongoing. |  | Complete |
| 62 | Define options to improve information sharing between agencies and the Courts | MoJ | Information sharing already occurs between the Family Court and the District Court. Further work on information sharing is being undertaken as part of MoJ’s ongoing policy work on domestic violence. | Part of 3.3 | First stage complete Ongoing 2008 & beyond |
| 63 | Simplify application forms for Protection orders | MoJ | The explanatory leaflet has been completed and will be placed on the Family Court’s Website. Copies will also be available through Courts. |  | Form complete. To be distributed |
| 64 | Improve the use of security resources available to courts | MoJ | The Ministry of Justice is currently preparing another new initiative bid for additional resources. It will also be reviewing how it uses existing resources to ensure it is getting best value for money. |  | First stage complete, Ongoing 2008 & beyond |
| 65 | Consider an office to provide DVA-specific legal services | LSA MoJ | Currently developing objective and milestones as part of business planning. |  | Ongoing 2008 & beyond |
| 66 | Determine level of attendance and performance of perpetrators at programmes | MoJ | The Ministry of Justice is currently collating and analysing data. A variation was submitted in July 2008, pending approval. The results from this will be used to inform Action 67. |  | Ongoing 2008 & beyond |
| 67 | Develop options to ensure perpetrators attend and complete programmes | MoJ | Further phase of Action 66. This action will not commence until Action 66 is completed (final report will be completed 30 September 2008). |  | Ongoing 2007/2008 & beyond |
| 68 | Information for perpetrators on programmes | Police | Information distributed |  | Complete |
| 70 | Ensure the range of programmes matches the profiles of perpetrators | Corrections / MoJ | Options to potentially address gaps in programmes for prisoners with DV-related offences formulated. Currently analysing these options. |  | Ongoing 2007/2008 & beyond |
| 71 | Local Case Collaboration (FVIARS) | CYF / Police | FVIARS phase one complete and evaluation complete, second phase - nationwide roll-out underway. | Informs 3.3 | Phase one complete, Ongoing 2008 & beyond |
| Effective Support Services |  |  |  |  |  |
| 72 | Govt investing $9 million over the next four years | MSD | 2006/2007 contracts complete and funding took place. Continued funding of contracts from baseline. |  | Dev. Complete Ongoing to 09/10 |
| 73 | Develop new funding model | MSD | Pathway to Partnership (P2P) developed and ongoing. $20.4 million allocated in 2007. $446 million announced 12 Feb 2008 to fund essential NGO child and family services. | 2.1 | Complete OPOA |
| 74 | Cost family violence and family support services | MSD | Costing tool developed as part of P2P as above. | 2.1 | Complete |
| 75 | Build on existing workforce and organisational development initiatives | MSD | P2P Funding announced on 12 Feb 2008 to build a sustainable NGO sector. Ongoing. | 2.1 | Dev. complete. Ongoing 2008 & beyond |
| 76 | Continue to promote the use of integrated contracts | MSD | Funding for Outcomes developed and implemented. These contracts now part of FACS core business under the Integrated Contracts team. |  | Complete |

# How this report works

The Ongoing Programme of Action Monitoring Report is organised into two sections:

- A summary section – which provides an overview of the key highlights over the previous two months, and identifies the hotspots that need to be monitored closely over the upcoming two months to ensure objectives remain on track.

- A monitoring report section – which includes two key parts:

    - Summary information from the project plans for each objective.

    - A summary of the progress of each objective over the last three months and an overview of the work that is expected to occur over the next three months.

The report format is still evolving. There are some objectives that require more ongoing information. The Secretariat will work to extend this information with each report.

We have tried to layer the information provided in the report so that Taskforce members can get a snapshot of where things are at and refer to the Monitoring Report section for more detail on each objective, its milestones, and the responsible project managers within each agency if they wish to follow up work or find out more information.

The Taskforce’s planning and reporting hierarchy consists of the following:

- Objectives – specific work that has been signalled in the programme of action

- Actions –  specific work signalled in the programme of action, as part of an objective and/or in the Taskforce’s work programme which sits beneath the programme of action

- Key Milestones – taken from individual agency project plans.

We have also introduced a formal variation process, which aims to:

- maintain the integrity of the Taskforce’s programme of action

- ensure there is transparent communication within the Taskforce about changes to objectives and/or actions

- ensure the objective and actions remain relevant to the Taskforce and its priorities.

The variation process is about to change. Agencies will be contacted once further work on this has been done. The variation process currently involves:

- completing the attached variation template

- consulting with appropriate Taskforce agencies over the changes to gain agreement and buy-in (this will be left to the responsible Taskforce agency seeking a variation to determine)

- sending a draft of the variation to the Secretariat to review before it is finalised, the Secretariat will then provide feedback and the variation can be finalised

- getting the responsible Taskforce member to sign the variation (thereby finalising the variation)

- sending the finalised variation to the Secretariat

- the Secretariat will brief the Taskforce Chair and seek his sign-off

- the Secretariat advise the agency seeking a variation of the outcome

- the outcome is noted in the Taskforce monitoring report.

A formal variation is required when a Taskforce agency wants to change an objective, action or both. Formal variations are not currently required to change key milestones. However, any key milestone changes must be provided to the Secretariat so that a log can be kept and changes can be tracked over time. Formal variations are not currently required for key milestones because these changes should not compromise work on an objective and its associated actions.

A formal variation needs to be completed if the deadline for completion of an objective and associated actions changes. This is because the overall objective and actions are compromised.

The variation template is attached to this report. An electronic copy can be obtained from the Taskforce Secretariat.

Reporting frequency

Ongoing Programme of Action Monitoring Reports will be produced for each Taskforce meeting. If a Taskforce meeting is changed to a workshop then a report will still be produced but will be circulated in hard copy only.

Other information

- The information in the monitoring report centres on the key milestone information provided by each Taskforce agency.

- To ensure the monitoring report remains current, as each milestone is reported complete it will be dropped from the report. The Secretariat will keep a record of all milestones so that this information can be used at a later date, if necessary.

| To | Peter Hughes | Date |  |
| --- | --- | --- | --- |
| From |  |  |  |
| Security Level | In Confidence |  |  |
| request to amend Work Programme Objective or Action |  |  |  |
| Action | For your approval |  |  |

I am seeking your approval to change an objective or action from the work programme for the Taskforce for Action on Violence within Families.

Current Deliverable:

[Insert Project / Work Programme Objective and/or Action]

[Insert current milestone/s (from project plan template)]

Changed to:

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project plan template)]

Reasons for a Variation Request

A variation to this deliverable has become necessary as:

- [please insert reason/s for variation]

Consultation

In seeking a variation to this deliverable, I have consulted with the following people:

| Name | Position and organisation |
| --- | --- |

Impact

The impacts in agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

The impacts in not agreeing to this change are:

- [add details of any impact such as reporting to Cabinet, other key project timeframes, budget initiatives, reputation, legislation.]

Recommendation

It is recommended that you:

- agree to a variation to an objective or action found in the Taskforce’s work programme

[Insert Project / Work Programme Objective and/or Action]

[Insert new milestone/s (also complete new project template)]

Approve / Decline

| Xxxxx (Taskforce representative) |  |  |
| --- | --- | --- |
| XXXXX (Taskforce agency) |  | Date |

| Peter Hughes |  |  |
| --- | --- | --- |
| Chair |  | Date |
| Approved  Not Approved  |  |  |

Note that the Inter-agency Plan references establishing an intensive, comprehensive behavioural service for 3 -7 year olds, the ongoing work programme discusses delivery to 3-8 year olds.